## BOQ
Bld. Part | Tra de | Item No | Sub No | Description | Unit | Qty | Unit rate | Amount
SPECIFICATION AND BILL OF QUANTITIES
Project Residencial building
A |  |  |  | A. SUBSTRUCTURE
A | 1 |  |  | Excavation and Earth Works | Birr |  |  | 6395.42
A | 2 |  |  | Concrete Works | Birr |  |  | 34877.8
A | 3 |  |  | Masonry works | Birr |  |  | 21445
A |  |  |  | Total A | Birr |  |  | 62718.22
B |  |  |  | B. SUPER STRUCTURE
B | 1 |  |  | Concrete Work | Birr |  |  | 16553.06
B | 2 |  |  | Block Work | Birr |  |  | 29852.55
B | 3 |  |  | Roofing | Birr |  |  | 21557.4
B | 4 |  |  | Carpentry & Joinery | Birr |  |  | 39117.1
B | 5 |  |  | Metal Works | Birr |  |  | 14280
B | 6 |  |  | Finishing Works | Birr |  |  | 39104.25
B | 7 |  |  | Glazing | Birr |  |  | 738.72
B | 8 |  |  | Painting | Birr |  |  | 9895.8
B | 9 |  |  | Sanitary Installation | Birr |  |  | 11525
B | 10 |  |  | Electrical Installation | Birr |  |  | 25800
T |  |  |  | Total B | Birr |  |  | 208423.88
T |  |  |  | SUBTOTAL A + B | Birr |  |  | 271142.1 | 1.1067
|  |  |  | Direct cost + indirect cost | Birr |  |  | 244991.446
A | 1 |  |  | SUB STRUCTURE
A | 1 |  |  | EXCAVATION & EARTH WORK
A | 1 | 1 |  | Site clearing and removing of the top soil 200 mm thick | m² | 250.74 | 3 | 752.22
A | 1 | 2 |  | Trench excavation in ordinary soil for masonry foundation to a depth of 1500 mm from reduced level. | m³ | 54.15 | 20 | 1083
A | 1 | 3 |  | Backfill under hard core with selected material from the site, well moistured and compacted in layers not exceeding 200 mm thickness in every layer | m³ | 26.06 | 25 | 651.5
A | 1 | 4 |  | 250 mm thick basaltic stone hardcore (delivered and prepared by the contractor) well consolidated and blinded with crushed stone. | m² | 130.29 | 30 | 3908.7
A | 1 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 6395.42
A | 2 |  |  | CONCRETE WORK
A | 2 | 1 |  | 50 mm lean concrete quality C-5, 150 kg of cement/m³:
A | 2 | 1 | 1 | Under masonry | m² | 27.06 | 37 | 1001.22
A | 2 | 2 |  | Reinforced concrete quality C-25, minimum cement content of 360 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately) |  |  |  | 0
A | 2 | 2 | 1 | In grade beams | m³ | 5.69 | 1200 | 6828
A | 2 | 3 |  | Reinforced concrete quality C-20, minimum cement content of 320 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately)
A | 2 | 3 | 1 | In 100 mm thick floor slab | m² | 161.68 | 110 | 17784.8
A | 2 | 4 |  | FORMWORK |  |  |  | 0
A | 2 | 4 |  | Provide, cut and fix in position sawn zigba wood or steel formwork which ever appropriate, including all necessary supports according Ethiopian Standards (BS) |  |  |  | 0
A | 2 | 4 | 1 | To grade beams | m² | 55.96 | 40 | 2238.4
A | 2 | 5 |  | Mild steel reinforcement according to structural drawings. Reinforcement shall be free from dirt, oil, grease, paint, retarders, etc and any other substances which may effect the reinforcement and concrete bond.
A | 2 | 5 | 1 | Dia 8 mm deformed bar | kg | 312.9585 | 15 | 4694.38
A | 2 | 5 | 2 | Dia 12 mm deformed bar | kg | 155.4 | 15 | 2331
A | 20 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 34877.8
A | 3 |  |  | MASONRY WORK
A | 3 | 1 |  | 400 mm thick basaltic stone masonry or equivalent, bedded in cement mortar mix (1:3) below ground surface. | m³ | 54.15 | 300 | 16245
A | 3 | 2 |  | 400 mm thick basaltic stone masonry or equivalent type of stone masonry roughly dressed, bedded in cement mortar mix (1:3) above ground surface. | m³ | 16.25 | 320 | 5200
A | 3 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 21445
B |  |  |  | SUPER STRUCTURE
B | 1 |  |  | CONCRETE WORK
B | 1 | 1 |  | Reinforced concrete quality C-25, minimum cement content of 360 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately)
B | 1 | 1 | 1 | In elevation columns | m³ | 1.98 | 1200 | 2376
B | 1 | 1 | 2 | In roof beams | m³ | 4.54 | 1200 | 5448
B | 1 | 2 |  | FORMWORK
B | 1 | 2 |  | Provide, cut and fix in position sawn zigba wood or steel formwork which ever appropriate, including all necessary supports according Ethiopian Standards (BS)
B | 1 | 2 | 1 | For elevation columns | m² | 10.32 | 65 | 670.8
B | 1 | 2 | 2 | For roof beams | m² | 55.96 | 65 | 3637.4
B | 1 | 3 |  | STEEL REINFORCEMENT
B | 1 | 3 |  | Mild steel reinforcement according to structural drawings. Reinforcement shall be free from dirt, oil, grease, paint, retarders, etc and any other substances which may effect the reinforcement and concrete bond.
B | 1 | 3 | 1 | Dia 8 mm deformed bar | kg | 77.6965 | 15 | 1165.45
B | 1 | 3 | 2 | Dia 12 mm deformed bar | kg | 217.0272 | 15 | 3255.41
B | 1 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 16553.06
B | 2 |  |  | BLOCK WORK
B | 2 | 1 | 1 | Class C 200 mm thick HCB wall which can satisfy the designed strength, bedded in cement mortar (1:3). | m² | 229.25 | 110 | 25217.5
B | 2 | 1 | 2 | Ditto, but 100 mm thick. | m² | 54.53 | 85 | 4635.05
B | 2 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 29852.55
B | 3 |  |  | ROOFING
B | 3 | 1 | 1 | Roof cover in precoated or galvanized sheet metal USG 30 fixed to timber purlins. Price shall include G-30 flat sheet development length = 310 mm ridge cap and UV resistant washers. (Purlins measured separately and roof measured in horizontal projections) | m² | 223.26 | 90 | 20093.4
B | 3 | 2 | 1 | Supply and fix G-30 galvanized flat metal sheet gutter as per the detail drawing. Price shall include all necessary accessories including metal bracket holders, one coat of anti rust and two coats of oil paint. Development length = 850 mm | m | 48.8 | 30 | 1464
B | 3 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 21557.4
B | 4 |  |  | CARPENTRY AND JOINERY
B | 4 | 1 |  | WOOD STRUCTURE
B | 4 | 1 |  | Supply, fabricate and mount wood truss according to the structural drawing. Price shall include two coat of anti-termite treatment. and all other necessary accessories. The connection joints shall be approved by the responsible engineer.
B | 4 | 1 | 1 | Eucalyptus wood Horizontal truss members. Size dia.100 mm | m | 358.15 | 12 | 4297.8
B | 4 | 1 | 2 | Eucalyptus wood vertical & diagonal truss members. Size dia.80 mm | m | 105.4 | 10 | 1054
B | 4 | 1 | 3 | Sawn zigba wood roof purlins placed at c/c 900 mm. Size 50 x 70 mm | m | 341.6 | 18 | 6148.8
B | 4 | 2 |  | CEILINGS WORKS |  |  |  | 0
B | 4 | 2 | 1 | Supply and fix 8 mm thick chip wood ceilings as per the engineers approval and according to the detail drawing. Price shall include 40 x 50 mm zigba wood battens with c/c spacing of 600 mm both ways, middle and corner strip and all other necessary accessory | m² | 135.3 | 120 | 16236
B | 4 | 2 | 2 | 0.8 mm thick ribbed sheet metal soffit cover | m² | 26.32 | 150 | 3948
B | 4 | 2 |  | FACIA BOARD |  |  |  | 0
B | 4 | 2 | 3 | Supply and fix Tid wood Facia board according to the detail drawing. Price shall include 3 coats of varnish paint. Size 20 x 250 mm. | m | 68.2 | 30 | 2046
B | 4 | 3 |  | Flush wooden door
B | 4 | 3 |  | Supply, delivery and fix doors manufactured 4mm play wood and stiffened properly, all as per the engineers approval, door schedule and detail drawing. The frames shall be designed and fixed to the plastering to allow the load on it.
B | 4 | 3 | 1 | Type D1: Size 900 x 2100 mm | No. | 3 | 1795.5 | 5386.5
B | 5 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 39117.1
B | 5 |  |  | METAL WORKS
B | 5 |  |  | Supply, delivery and fix doors and windows manufactured from 28 x 1 mm LTZ profile, all as per the engineers approval and window door schedule and detail drawing. The frames shall be designed and fixed to the plastering to allow the load on the door.
B | 5 | 1 |  | DOORS
B | 5 | 1 | 1 | Type D1: Size 900 x 2100 mm | No. | 5 | 850.5 | 4252.5
B | 5 | 1 | 2 | Type D2: Size 700 x 2100 mm | No. | 5 | 661.5 | 3307.5
B | 5 | 2 |  | WINDOWS
B | 5 | 2 | 1 | Type W1: 1000 x 1200 mm | No. | 5 | 480 | 2400
B | 5 | 2 | 2 | Type W2: 1800 x 1200 mm | No. | 5 | 864 | 4320
B | 5 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 14280
B | 6 |  |  | FINISHING WORKS
B | 6 | 1 |  | Apply three coats of plastering in cement mortar (1:3).
B | 6 | 1 | 1 | To internal wall surface | m² | 324.03 | 32 | 10368.96
B | 6 | 1 | 2 | To external wall surface | m² | 191.37 | 32 | 6123.84
B | 6 | 1 | 3 | Apply two coats of plastering in cement mortar (1:3) to receive ceramic wall tile. Price shall include supply, pre-cleaning and preparation of the surface. | m² | 62.25 | 27 | 1680.75
B | 6 | 2 |  | Flooring
B | 6 | 2 | 1 | 48 mm thick trowel finished cement sand screed (1:3) t receive PVC tile | m² | 18 | 55 | 990
B | 6 | 2 | 2 | PVC floor tile, 2 mm thick | m² | 18 | 90 | 1620
B | 6 | 2 | 3 | PVC skirting, 60 mm wide | m² | 54.6 | 12 | 655.2
B | 6 | 2 | 4 | Terrazzo floor tile, 20 mm thick. Price shall include supply, 30 mm cement screeding and other preparations | m² | 54 | 120 | 6480
B | 6 | 2 | 5 | Terrazzo skirting stuck to wall, 100 mm wide. Price shall include supply, pre-cleaning and other preparation of the surface | m² | 85.8 | 18 | 1544.4
B | 6 | 3 |  | Wall tile |  |  |  | 0
B | 6 | 3 | 1 | 6 mm thick white ceramic wall tile | m² | 62.25 | 110 | 6847.5
B | 6 | 4 |  | PAVING |  |  |  | 0
B | 6 | 4 | 1 | 600 mm wide stone pavement around the building. Price shall include red ash or equivalent bedding material and half dia 400 mm concrete rain water pipe pointing as per the detail drawing and the engineers direction. | m² | 23.28 | 120 | 2793.6
B | 6 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 39104.25
B | 7 |  |  | GLAZING
B | 7 | 1 | 1 | Supply and fix 4 mm thick clear sheet glass to metal beads and puttied with approved quality of putty. |  | 10.26 | 72 | 738.72
B | 7 |  |  | TOTAL CARRIED TO SUMMARY | m² |  |  | 738.72
B | 8 |  |  | PAINTING
B | 8 | 1 |  | Provide and apply three coats emulsion paint All required materials as per approval of the engineer.
B | 8 | 1 | 1 | to internal wall surfaces flushed finished | m² | 324.03 | 15 | 4860.45
B | 8 | 1 | 2 | to external plastered wall surfaces. | m² | 191.37 | 15 | 2870.55
B | 8 | 1 | 3 | to chip wooden ceiling | m² | 135.3 | 16 | 2164.8
B | 8 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 9895.8
B | 9 |  |  | SANITARY INSTALLATION
B | 9 |  |  | SANITARY EQUIPMENT (FIXTURES)
B | 9 | 1 | 1 | Supply and fix Awassa ceramics hand wash basins made of white vitreous china, with chrome plated cold and hot water mixer, complete with plug, chrome plated chain holder, P-smell trap with connection pipe and with all other necessary accessories. Size 405x500 mm | No. | 2 | 600 | 1200
B | 9 | 1 | 2 | Supply and fix Awassa ceramics wash down water closets made of white vitreous china with plastic seat and cover including low flush cistern. Complete with all necessary accessories | No. | 2 | 800 | 1600
B | 9 | 1 | 3 | Supply and fix Awassa ceramics toilet paper holder with chrome plated brass wall flanged roll with chrome plated fastening screws and other accessories. | No. | 2 | 50 | 100
B | 9 | 1 | 4 | Supply and fix soap holder out of Awassa ceramic or equivalent, fixed with chrome plated brass wall flanged roll chrome plated fastening screws and other accessories. Size: 305 x 150 mm | No. | 4 | 50 | 200
B | 9 | 1 | 5 | Supply and fix Enameled cast iron shower unit, with chrome plated valves and shower head and other accessories. Size: 700x700 mm | No. | 2 | 600 | 1200
B | 9 | 1 | 6 | Supply and fix Kitchen Single boul sink out of stainless steel, with chrome plated Mixing tape, complete with plug, chrome plated chain holder and other accessories. Size: 1200x500 mm | No. | 2 | 900 | 1800
B | 9 | 1 | 7 | Supply and fix floor drains made of polished steel of approved quality, complete with P-smell trap and all other necessary fittings and accessories. Size: - Dia. 50 mm | No. | 2 | 90 | 180
B | 9 | 1 | 8 | Supply and fix glass mirror complete with chrome plated brass frames and screws and all necessary accessories. Price shall include all civil works. Size: 500 x 400 mm | No. | 2 | 120 | 240
B | 9 | 2 |  | WATER SUPPLY PIPES AND VALVES
B | 9 | 2 |  | Water pipes shall be galvanized steel and be fixed to, walls, beams or etc. Unit price shall include all assistance civil works and necessary fittings such as T- bends and Y- reducers. Gate valves and other necessary valves shall be fixed properly as per
B | 9 | 2 |  | Supply and install galvanized steel pipes to internal water distribution system as shown on the drawing complete with all the necessary accessories.
B | 9 | 2 | 1 | Dia. 15 mm | m | 12 | 15 | 180
B | 9 | 3 |  | VALVES
B | 9 | 3 |  | Supply and fix approved quality brass gate valves at internal branch water pipes and pipe inlet to building of the following sizes and as where shown on the drawing.
B | 9 | 3 | 1 | Dia. 15 mm | No. | 4 | 30 | 120
B | 9 | 4 |  | WASTE, VENT AND RAIN WATER PIPES AND ACCESSORIES
B | 9 | 4 |  | All domestic waste, vent and storm water pipe lines shall be PVC pipes and provided with a minimum slope of 2% towards the outlet. All PVC pipes and necessary fittings shall be standard quality and be free from damage during storage, construction and etc.
B | 9 | 4 |  | Supply and lay internal PVC waste and vent pipes according to where shown on the drawings. Complete with all the necessary fittings.
B | 9 | 4 | 1 | Dia. 50 mm | m | 7 | 30 | 210
B | 9 | 4 | 2 | Dia. 110 mm | m | 3.5 | 50 | 175
B | 9 | 5 |  | Supply and lay approved quality storm water galvanized sheet metal down pipes according to where shown on the drawing. Price shall include all the necessary connecting pieces. |  |  |  | 0
B | 9 | 5 | 1 | Dia. 100 x 80 mm | m | 24 | 30 | 720
B | 9 | 6 | 1 | Manhole out of internally plastered stone masonry/ HCB wall with 80 mm thick mass concrete base slab and 80 mm RC over. Price shall include all required works. Size: 600 x 600 x 700 mm inner diameter | No. | 3 | 1200 | 3600
B | 9 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 11525
B | 10 |  |  | ELLECTRICAL INSTALLATION WORKS
B | 10 | 1 |  | SUPPLY AND INSTALL
B | 10 | 3 |  | CONDUITS AND PIPES
B | 10 | 3 | 1 | Supply and install PVC pipe of 36 mm diameter | m | 90 | 90 | 8100
B | 10 | 4 |  | DISTRIBUTION BOARDS
B | 10 | 4 | 1 | Flush mounting distribution board MDB1, in sheet steel enclosure with lockable door and with phase, neutral, earth bus-bars of 63A/3P and consisting of:- 1 pc main ACB of 63A/3P 1 pc ACB of 32A/3P 13 pcs ACB of 16A/1P 1 pc ACB of 10A/1P 25% reserve p | No. | 1 | 1000 | 1000
B | 10 | 5 |  | LIGHT POINTS
B | 10 | 5 | 1 | Supply and install flush mounted light points fed through PVC insulated conductors of 3 x 2.5 mm² inside PVC conduits of 16 mm diameter, including junction boxes with covers insulating screw cap connectors. | No. | 15 | 120 | 1800
B | 10 | 6 |  | Switches
B | 10 | 6 | 1 | Flush mounting single switch, 7740 01 + 774041 | No. | 10 | 50 | 500
B | 10 | 6 | 3 | Flush mounting two-way switch, 7740 06 + 774041 | No. | 10 | 70 | 700
B | 10 | 7 |  | SOCKET OUTLET POINTS |  |  |  | 0
B | 10 | 7 | 1 | Supply and install 10-16A/1P socket outlet points fed through PVC insulated conductors of 3 x 2.5 mm² inside PVC conduits of 16 mm diameter including junction boxes with covers, and insulating screw cap connectors all for flush mounting. | No. | 10 | 120 | 1200
B | 10 | 7 |  | SOCKET OUTLETS
B | 10 | 7 |  | Supply and install socket Outlets (Type Legrand Suno or Equivalent)
B | 10 | 7 | 1 | Flush mounting socket outlet of 10A/1P, 774020+774041 | No. | 10 | 50 | 500
B | 10 | 8 |  | LIGHT FITTINGS AND LAMPS
B | 10 | 8 |  | Supply and install Light Fittings and Lamps (Specified Type or Equivalent)
B | 10 | 8 | 1 | Fluorescent fitting type PhilipsTMS 022/136 I +2 x TLD 36W/840 lamps | No. | 5 | 800 | 4000
B | 10 | 8 | 2 | Incandescent fitting type RZB 22147.912 + TC 9W lamp | No. | 10 | 800 | 8000
B | 10 |  |  | TOTAL CARRIED TO SUMMARY |  |  |  | 25800

## Productivity
ITEM | DESCRIPTION | UNIT | QTY | Resource | Performance | Qty
[5 empty] | unit/hr | Units
02. EXCAVATION AND EARTH WORK
Excavation Soil type shall be
all as per the attached soil report.
Pit excavation
01 | Remove top soil depth 30cm | m2 | 174 | Daily laborer | 0.625 | 278.4
|  |  |  | Gang leader | 9.375 | 18.56
02 | Pit not exceeding 1.5m | m3 | 112 | Daily laborer | 0.125 | 896
|  |  |  | Gang leader | 1.875 | 59.7333
03 | Over 1.5m not exceeding | m3 | 60 | Daily laborer | 0.1125 | 533.3333
|  |  |  | Gang leader | 1.6875 | 35.5556
Fill
04 | Selected borrowed fill | m3 | 152 | Daily laborer | 0.1125 | 1351.1111
|  |  |  | Gang leader | 1.6875 | 90.0741
|  |  |  | Compactor | 1.6875 | 90.0741
|  |  |  | Selected material (m3) | 1.2 | 182.4
05 | Disposal | m3 | 56 | Wheel loader | 48 | 1.1667
|  |  |  | Dump truck | 12 | 4.6667
Sub base
06 | Hard core 25cm. thick | m2 | 103 | Mason | 0.75 | 137.3333
|  |  |  | Daily laborer | 0.375 | 274.6667
|  |  |  | Basaltic stone | 0.34 | 302.9412
TOTAL TO SUMMARY……………………BIRR
03. CONCRETE WORK
Insitu concrete
01 | Plain blinding concrete C - 5 | m3 | 3 | Mason | 1.5625 | 1.92
|  |  |  | Daily laborer | 87.5 | 0.034286
|  |  |  | Gang leader | 3.125 | 0.96
|  |  |  | Mixer | 3.125 | 0.96
|  |  |  | Gravel | 0.9 | 3.3333
|  |  |  | Sand | 0.48 | 6.25
|  |  |  | Cement | 1.5 | 2
Ordinary portland cement
Reinforced sub structure concrete
02 | C -25, in footing | m3 | 17 | Mason | 1.5625 | 10.88
|  |  |  | Daily laborer | 87.5 | 0.19429
|  |  |  | Gang leader | 3.125 | 5.44
|  |  |  | Mixer | 3.125 | 5.44
|  |  |  | Vibrator | 1.5625 | 10.88
|  |  |  | Gravel | 0.9 | 18.8889
|  |  |  | Sand | 0.48 | 35.4167
|  |  |  | Cement | 1.5 | 11.3333
03 | C - 25, in grade column | m3 | 1 | Mason | 1.5625 | 0.64
|  |  |  | Daily laborer | 87.5 | 0.011429
|  |  |  | Gang leader | 3.125 | 0.32
|  |  |  | Mixer | 3.125 | 0.32
|  |  |  | Vibrator | 1.5625 | 0.64
|  |  |  | Gravel | 0.9 | 1.1111
|  |  |  | Sand | 0.48 | 2.0833
|  |  |  | Cement | 1.5 | 0.66667
04 | C - 25 in grade beam | m3 | 4 | Mason | 1.5625 | 2.56
|  |  |  | Daily laborer | 87.5 | 0.045714
|  |  |  | Gang leader | 3.125 | 1.28
|  |  |  | Mixer | 3.125 | 1.28
|  |  |  | Vibrator | 1.5625 | 2.56
|  |  |  | Gravel | 0.9 | 4.4444
|  |  |  | Sand | 0.48 | 8.3333
|  |  |  | Cement | 1.5 | 2.6667
05 | C - 15 in G . F slab | m3 | 11 | Mason | 1.5625 | 7.04
|  |  |  | Daily laborer | 87.5 | 0.12571
|  |  |  | Gang leader | 3.125 | 3.52
|  |  |  | Mixer | 3.125 | 3.52
|  |  |  | Vibrator | 1.5625 | 7.04
|  |  |  | Gravel | 0.8 | 13.75
|  |  |  | Sand | 0.48 | 22.9167
|  |  |  | Cement | 2.8 | 3.9286
Reinforced super structure
06 | C - 25 in elevation column | m3 | 2 | Mason | 1.5625 | 1.28
|  |  |  | Daily laborer | 87.5 | 0.022857
|  |  |  | Gang leader | 3.125 | 0.64
|  |  |  | Mixer | 3.125 | 0.64
|  |  |  | Vibrator | 1.5625 | 1.28
|  |  |  | Gravel | 0.9 | 2.2222
|  |  |  | Sand | 0.48 | 4.1667
|  |  |  | Cement | 1.5 | 1.3333
07 | C-25 in beams & lentil | m3 | 6 | Mason | 1.5625 | 3.84
|  |  |  | Daily laborer | 87.5 | 0.068571
|  |  |  | Gang leader | 3.125 | 1.92
|  |  |  | Mixer | 3.125 | 1.92
|  |  |  | Vibrator | 1.5625 | 3.84
|  |  |  | Gravel | 0.9 | 6.6667
|  |  |  | Sand | 0.48 | 12.5
|  |  |  | Cement | 1.5 | 4
08 | C-25 in roof slab | m3 | 18 | Mason | 1.5625 | 11.52
|  |  |  | Daily laborer | 87.5 | 0.20571
|  |  |  | Gang leader | 3.125 | 5.76
|  |  |  | Mixer | 3.125 | 5.76
|  |  |  | Vibrator | 1.5625 | 11.52
|  |  |  | Gravel | 0.9 | 20
|  |  |  | Sand | 0.48 | 37.5
|  |  |  | Cement | 1.5 | 12
09 | C -25 in parapet | m3 | 3 | Mason | 1.5625 | 1.92
|  |  |  | Daily laborer | 87.5 | 0.034286
|  |  |  | Gang leader | 3.125 | 0.96
|  |  |  | Mixer | 3.125 | 0.96
|  |  |  | Vibrator | 1.5625 | 1.92
|  |  |  | Gravel | 0.9 | 3.3333
|  |  |  | Sand | 0.48 | 6.25
|  |  |  | Cement | 1.5 | 2
10 | C-25 water tight concrete in average 15cm thick over roof
slab including dia.4mm steel bar at c/c 20cm both way to
be finished with smooth trowel finish to the given slope and
| make ready to apply water proofing material. | m2 | 146 | Mason | 1.5625 | 93.44
|  |  |  | Daily laborer | 87.5 | 1.6686
|  |  |  | Gang leader | 3.125 | 46.72
|  |  |  | Mixer | 3.125 | 46.72
|  |  |  | Vibrator | 1.5625 | 93.44
|  |  |  | Gravel | 0.9 | 162.2222
|  |  |  | Sand | 0.48 | 304.1667
|  |  |  | Cement | 1.5 | 97.3333
Form work
Sub structure normal finish to:-
11 | Footing | m2 | 33
12 | Foundation column | m2 | 19
13 | Grade beam | m2 | 38
Super structure normal finish to:-
14 | Elevation column | m2 | 35
15 | Beams & lintels | m2 | 71
16 | Roof slab | m2 | 134
17 | Parapet | m2 | 37
Reinforcement
Sub structure
18 | Diameter 8mm | kg | 570
19 | Diameter 12 - 20mm | kg | 1559
Super Structure
20 | Diameter 8mm | kg | 1020
21 | Diameter 18 - 20mm | kg | 1139
Concrete ancillaries
Expansion joint
22 | In 8 cm thick chip wood depth 10cm | m | 82
| TOTAL TO SUMMARY - - - - - - - | BIRR
04. MASONRY WORK
Hollow concrete block work above
Grade wall in cement mortar Class "A"
01 | 20cm thick both face left for plaster | m2 | 190
| TOTAL TO SUMMARY - - - - - - - | BIRR
05. ROOF WATER PROOFING
01 | Decadex FL-10 water proofing system embodiments
coat = 0.5 liter/m2 premium grade reemat glass mat
reinforcement, top coat = 0.5 liter/m2 and all according
| to manufacture instruction. | m2 | 146
| TOTAL TO SUMMARY - - - - - - - - | BIRR
07. JOINERY
Finish wooden doors kerrero
01 | Type D3 size 90 x 250cm. | Nº | 2
| TOTAL TO SUMMARY - - - - - - - - | BIRR
10. METAL WORK
Metal doors & windows LTZ black
sheet profile 38mm and 1.5 mm thick
door
01 | Type D1 size 300 x 250 cm | Nº | 1
02 | Type D2 size 120 x 250 cm | Nº | 1
Windows
03 | Type W2 size 120 x 120 cm | Nº | 4
Metal louver
04 | Type W1 size 140 x 140 cm | Nº | 2
05 | Type W3 size 90 x 90cm | Nº | 9
| TOTAL TO SUMMARY - - - - - - - - - | BIRR
11. FINISHING
11.1 PLASTERING
Two coats of plaster cement mortar
to internal surface of:-
01 | Hollow concrete block wall surface | m2 | 238
02 | Concrete vertical surface | m2 | 45
03 | Concrete soffit | m2 | 134
Cement mortal to external surface of:-
04 | Hollow concrete block wall surface | m2 | 142
05 | Concrete vertical surface | m2 | 82
Fine coat cement plaster to:-
06 | Internal plastered vertical surface | m2 | 283
07 | Concrete soffit | m2 | 134
Final render coat to:-
08 | External plastered vertical surface | m2 | 224
| TOTAL TO SUMMARY - - - - - - - - - | BIRR
11.2 FLOOR & WALL FINISH
Cement screed floor finish
01 | 5 cm thick smooth finished | m2 | 103
Sill
02 | Size:- 27 x 10cm concrete | m | 18
Concrete paving
03 | 10cm thick precast concrete | m2 | 43
| TOTAL TO SUMMARY - - - - - - - - - | BIRR
12. PAINTING
Plastic emultion paint
01 | Internal plastered vertical surface | m2 | 142
02 | Concrete soffit | m2 | 134
03 | External rendered surface | m2 | 224
| TOTAL TO SUMMARY - - - - - - - - - | BIRR
13. GLAZING
Transparent glass
Clear sheet
01 | 4mm thick | m2 | 2
TOTAL TO SUMMARY - - - - - - - - -
15. ELECTRICAL INSTALLATION
01 | Flush mounted sub-distribution board SDB-GE
consisting of:-
1pc main MCB of 20A, 1ph
1pc MCB of 10A, 1ph
| 1pc MCB of 10A, 1ph | Nº | 2
02 | Light points in thermoplastic conduit of
Diameter 13.5mm fed by PVC conductor
| of 3 x 2.5sq.mm | Nº | 8
03 | Single pole switch for recessed installation | Nº | 6
04 | Socket outlet in thermoplastic conduit of diameter 16mm fed
| by PVC conductor of 3 x 2.5sq.mm. | Nº | 6
05 | PVC cable 2 x 4 sq.mm in thermoplastic conduit of diameter
| 16mm. | ml | 40
06 | Philips TMS 012/236 with 2 x 'TL'D 36W
| fluorescent lamp | Nº | 8
TOTAL TO SUMMARY - - - - - - - - -

## Material Breakdown
Material breack down
Project Residencial building
Bld. Part | Tra de | Item No | Sub No | Description | Unit | Qty | Labour | hrs | Daily wage | Total amount | Material | qty | Unit rate | Total amount | Equipment | hrs | Unit rate | Total amount | Direct unit rate
A | 1 |  |  | SUB STRUCTURE
A | 1 |  |  | EXCAVATION & EARTH WORK
A | 1 | 1 |  | Site clearing and removing of the top soil 200 mm thick | m² | 250.74 | Daily laborer | 335 | 26 | 1088.75 |  |  | 0 | 0 |  |  | 0 | 0 | 4.7661 | 1195.0575
[7 empty] | Gang leader | 17 | 39 | 82.875 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 1 | 2 |  | Trench excavation in ordinary soil for masonry foundation to a depth of 1500 mm from reduced level. | m³ | 54.15 | Daily laborer | 271 | 26 | 880.75 |  |  | 0 | 0 |  |  | 0 | 0 | 17.8759 | 967.98
[7 empty] | Gang leader | 14 | 39 | 68.25 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 1 | 3 |  | Backfill under hard core with selected material from the site, well moistured and compacted in layers not exceeding 200 mm thickness in every layer | m³ | 26.06 | Daily laborer | 27 | 26 | 87.75 | Fuel (lit) | 14.5936 | 5.41 | 78.9514 | Plate compactor | 20.848 | 7 | 145.936 | 13 | 338.7801
[7 empty] | Gang leader | 2 | 39 | 9.75 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 2 | 39 | 9.75 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 1 | 4 |  | 250 mm thick basaltic stone hardcore (delivered and prepared by the contractor) well consolidated and blinded with crushed stone. | m² | 130.29 | Daily laborer | 87 | 26 | 282.75 | Basaltic stone (m3) | 45.6015 | 80 | 3648.12 |  |  | 0 | 0 | 32.033 | 4173.5799
[7 empty] | Gang leader | 9 | 39 | 43.875 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Mason | 18 | 52 | 117 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 1 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 |  |  | CONCRETE WORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 1 |  | 50 mm lean concrete quality C-5, 150 kg of cement/m³: |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 1 | 1 | Under masonry | m² | 27.06 | Daily laborer | 46 | 26 | 149.5 | Cement (qtl) | 3 | 174.771 | 524.3129 | Stationary mixer 350 lit | 3 | 30 | 90 | 54.1189 | 1464.4578
[7 empty] | Gang leader | 3 | 39 | 14.625 | Crushed aggregate, 20 mm (m3) | 2 | 262.385 | 524.77 |  |  | 0 | 0 |  | 0
[7 empty] | Mason | 5 | 52 | 32.5 | Sand (m3) | 1 | 80 | 80 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 3 | 39 | 14.625 | Fuel (lit) | 1 | 5.41 | 5.41 |  |  | 0 | 0 |  | 0
A | 2 | 2 |  | Reinforced concrete quality C-25, minimum cement content of 360 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 2 | 1 | In grade beams | m³ | 5.69 | Daily laborer | 80 | 26 | 260 | Cement (qtl) | 22.76 | 174.771 | 3977.7875 | Stationary mixer 350 lit | 3 | 30 | 90 | 1044.6273 | 5943.9292
[7 empty] | Gang leader | 3 | 39 | 14.625 | Crushed aggregate, 20 mm (m3) | 4.4382 | 262.385 | 1164.5171 | Vibrator | 5 | 7 | 35 |  | 0
[7 empty] | Mason | 5 | 52 | 32.5 | Sand (m3) | 2.9588 | 80 | 236.704 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 3 | 39 | 14.625 | Fuel (lit) | 0.3 | 5.41 | 1.623 |  |  | 0 | 0 |  | 0
A | 2 | 3 |  | Reinforced concrete quality C-20, minimum cement content of 320 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 3 | 1 | In 100 mm thick floor slab | m² | 161.68 | Daily laborer | 943 | 26 | 3064.75 | Cement (qtl) | 56.588 | 174.771 | 9889.9401 | Stationary mixer 350 lit | 65 | 30 | 1950 | 129.4612 | 20931.285
[7 empty] | Gang leader | 28 | 39 | 136.5 | Crushed aggregate, 20 mm (m3) | 12.9344 | 262.385 | 3393.7925 | Vibrator | 130 | 7 | 910 |  | 0
[7 empty] | Mason | 55 | 52 | 357.5 | Sand (m3) | 8.084 | 80 | 646.72 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 28 | 39 | 136.5 | Fuel (lit) | 6.5 | 5.41 | 35.165 |  |  | 0 | 0 |  | 0
A | 2 | 4 |  | FORMWORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 4 |  | Provide, cut and fix in position sawn zigba wood or steel formwork which ever appropriate, including all necessary supports according Ethiopian Standards (BS) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 4 | 1 | To grade beams, errection | m² | 55.96 | Daily laborer | 56 | 26 | 182 | Panel (m2hrs) | 447.68 | 0.1 | 44.768 |  |  | 0 | 0 | 74.1031 | 4146.8109
[7 empty] | Carpenter | 28 | 52 | 182 | Eucalyptus diam 8 cm (ml) | 11.7516 | 4.7421 | 55.7273 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 28 | 39 | 136.5 | Eucalyptus Diam. 10 cm (ml) | 167.88 | 5.2421 | 880.0444 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 16.788 | 12.0803 | 202.8037 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Mould Oil (lit) | 3.3576 | 1 | 3.3576 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Timber 2.5 cm thick (m3) | 0.5596 | 4250 | 2378.3 |  |  | 0 | 0 |  | 0
A | 2 | 4 | 2 | To grade beams, dismantling | m² | 55.96 | Daily laborer | 12 | 26 | 39 |  |  | 0.1 | 0 |  |  | 0 | 0 | 1.9549 | 109.395
[7 empty] | Carpenter | 6 | 52 | 39 |  |  | 4.7421 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 6 | 39 | 29.25 |  |  | 5.2421 | 0 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 12.0803 | 0 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 1 | 0 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 4250 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 5 |  | Mild steel reinforcement according to structural drawings. Reinforcement shall be free from dirt, oil, grease, paint, retarders, etc and any other substances which may effect the reinforcement and concrete bond. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 5 | 1 | Dia 6 mm deformed bar | kg | 0 | Daily laborer | 0 | 26 | 0 | Rebar diam 6 mm (kg) | 0 | 10.4253 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Bar-bender | 0 | 52 | 0 | black steel wire diam 1.5 mm (kg) | 0 | 12.0803 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 0 | 39 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 5 | 2 | Dia 8 mm deformed bar | kg | 312.9585 | Daily laborer | 29 | 26 | 94.25 | Rebar diam 8 mm (kg) | 319.2177 | 10.4253 | 3327.932 |  |  | 0 | 0 | 11.6596 | 3648.9679
[7 empty] | Bar-bender | 7 | 52 | 45.5 | black steel wire diam 1.5 mm (kg) | 6.2592 | 12.0803 | 75.6125 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 7 | 39 | 34.125 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 2 | 5 | 3 | Dia 12 mm deformed bar | kg | 155.4 | Daily laborer | 14 | 26 | 45.5 | Rebar diam 12 mm (kg) | 158.508 | 10.4253 | 1652.4895 |  |  | 0 | 0 | 11.6902 | 1816.6557
[7 empty] | Bar-bender | 4 | 52 | 26 | black steel wire diam 1.5 mm (kg) | 3.108 | 12.0803 | 37.5455 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 4 | 39 | 19.5 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 20 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 3 |  |  | MASONRY WORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
A | 3 | 1 |  | 400 mm thick basaltic stone masonry or equivalent, bedded in cement mortar mix (1:3) below ground surface. | m³ | 54.15 | Daily laborer | 362 | 26 | 1176.5 | Tracheatic stone (m3) | 64.98 | 80 | 5198.4 | Stationary mixer 350 lit | 2 | 30 | 60 | 362.7562 | 19643.2509
[7 empty] | Mason | 181 | 52 | 1176.5 | Cement (qtl) | 54.15 | 174.771 | 9463.8485 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant mason | 181 | 39 | 882.375 | Sand (m3) | 16.245 | 80 | 1299.6 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.16 | 5.41 | 0.8656 |  |  | 0 | 0 |  | 0
A | 3 | 2 |  | 400 mm thick basaltic stone masonry or equivalent type of stone masonry roughly dressed, bedded in cement mortar mix (1:3) above ground surface. | m³ | 16.25 | Daily laborer | 130 | 26 | 422.5 | Tracheatic stone (m3) | 19.5 | 80 | 1560 | Stationary mixer 350 lit | 1 | 30 | 30 | 375.5066 | 6101.9829
[7 empty] | Mason | 65 | 52 | 422.5 | Cement (qtl) | 16.25 | 174.771 | 2840.0284 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant mason | 65 | 39 | 316.875 | Sand (m3) | 4.875 | 80 | 390 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.08 | 5.41 | 0.4328 |  |  | 0 | 0 |  | 0
A | 3 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B |  |  |  | SUPER STRUCTURE |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 |  |  | CONCRETE WORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 1 |  | Reinforced concrete quality C-25, minimum cement content of 360 kg of cement/m³ filled in to form work and vibrated around rod reinforcement (formwork and reinforcement measured separately) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 1 | 1 | In elevation columns | m³ | 1.98 | Daily laborer | 28 | 26 | 91 | Cement (qtl) | 7.92 | 174.771 | 1384.1861 | Stationary mixer 350 lit | 1 | 30 | 30 | 1045.7949 | 2070.674
[7 empty] | Gang leader | 1 | 39 | 4.875 | Crushed aggregate, 20 mm (m3) | 1.5444 | 262.385 | 405.2274 | Vibrator | 2 | 7 | 14 |  | 0
[7 empty] | Mason | 2 | 52 | 13 | Sand (m3) | 1.0296 | 80 | 82.368 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 1 | 39 | 4.875 | Fuel (lit) | 0.1 | 5.41 | 0.541 |  |  | 0 | 0 |  | 0
B | 1 | 1 | 2 | In roof beams | m³ | 4.54 | Daily laborer | 64 | 26 | 208 | Cement (qtl) | 18.16 | 174.771 | 3173.841 | Stationary mixer 350 lit | 2 | 30 | 60 | 1041.2189 | 4727.1336
[7 empty] | Gang leader | 2 | 39 | 9.75 | Crushed aggregate, 20 mm (m3) | 3.5412 | 262.385 | 929.1578 | Vibrator | 4 | 7 | 28 |  | 0
[7 empty] | Mason | 4 | 52 | 26 | Sand (m3) | 2.3608 | 80 | 188.864 |  |  | 0 | 0 |  | 0
[7 empty] | SE Operator | 2 | 39 | 9.75 | Fuel (lit) | 0.2 | 5.41 | 1.082 |  |  | 0 | 0 |  | 0
B | 1 | 2 |  | FORMWORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 2 |  | Provide, cut and fix in position sawn zigba wood or steel formwork which ever appropriate, including all necessary supports according Ethiopian Standards (BS) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 2 | 1 | For elevation columns | m² | 10.32 | Daily laborer | 11 | 26 | 35.75 | Panel (m2hrs) | 82.56 | 0.1 | 8.256 |  |  | 0 | 0 | 40.4645 | 417.5941
[7 empty] | Carpenter | 6 | 52 | 39 | Eucalyptus diam 8 cm (ml) | 2.1672 | 4.7421 | 10.2771 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 6 | 39 | 29.25 | Eucalyptus Diam. 10 cm (ml) | 47.472 | 5.2421 | 248.8531 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 3.096 | 12.0803 | 37.4005 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Mould Oil (lit) | 0.6192 | 1 | 0.6192 |  |  | 0 | 0 |  | 0
B | 1 | 2 | 2 | For roof beams, errection | m² | 55.96 | Daily laborer | 56 | 26 | 182 | Panel (m2hrs) | 447.68 | 0.1 | 44.768 |  |  | 0 | 0 | 91.8001 | 5137.1318
[7 empty] | Carpenter | 28 | 52 | 182 | Eucalyptus diam 8 cm (ml) | 117.516 | 4.7421 | 557.2731 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 28 | 39 | 136.5 | Eucalyptus Diam. 10 cm (ml) | 257.416 | 5.2421 | 1349.4014 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 16.788 | 12.0803 | 202.8037 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Mould Oil (lit) | 3.3576 | 1 | 3.3576 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Timber 2.5 cm thick (m3) | 0.5596 | 4250 | 2378.3 |  |  | 0 | 0 |  | 0
B | 1 | 2 | 2 | For roof beams, dismantling | m² | 55.96 | Daily laborer | 56 | 26 | 36.4 |  |  | 0.1 | 0 |  |  | 0 | 0 | 1.8246 | 102.102
[7 empty] | Carpenter | 28 | 52 | 36.4 |  |  | 4.7421 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 28 | 39 | 27.3 |  |  | 5.2421 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 |  | STEEL REINFORCEMENT |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 |  | Mild steel reinforcement according to structural drawings. Reinforcement shall be free from dirt, oil, grease, paint, retarders, etc and any other substances which may effect the reinforcement and concrete bond. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 | 1 | Dia 6 mm plain bar | kg | 0 | Daily laborer | 0 | 26 | 0 | Rebar diam 6 mm (kg) | 0 | 10.4253 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Bar-bender | 0 | 52 | 0 | black steel wire diam 1.5 mm (kg) | 0 | 12.0803 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 0 | 39 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 | 2 | Dia 8 mm deformed bar | kg | 77.6965 | Daily laborer | 7 | 26 | 22.75 | Rebar diam 8 mm (kg) | 79.2504 | 10.4253 | 826.2075 |  |  | 0 | 0 | 11.6902 | 908.289
[7 empty] | Bar-bender | 2 | 52 | 13 | black steel wire diam 1.5 mm (kg) | 1.5539 | 12.0803 | 18.7719 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 2 | 39 | 9.75 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 | 3 | Dia 10 mm deformed bar | kg | 0 | Daily laborer | 0 | 26 | 0 | Rebar diam 10 mm (kg) | 0 | 10.4253 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Bar-bender | 0 | 52 | 0 | black steel wire diam 1.5 mm (kg) | 0 | 12.0803 | 0 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 0 | 39 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 | 3 | 4 | Dia 12 mm deformed bar | kg | 217.0272 | Daily laborer | 20 | 26 | 65 | Rebar diam 12 mm (kg) | 221.3677 | 10.4253 | 2307.8196 |  |  | 0 | 0 | 11.6657 | 2531.7722
[7 empty] | Bar-bender | 5 | 52 | 32.5 | black steel wire diam 1.5 mm (kg) | 4.3405 | 12.0803 | 52.435 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant bar-bender | 5 | 39 | 24.375 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 1 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 2 |  |  | BLOCK WORK |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 2 | 1 | 1 | Class C 200 mm thick HCB wall which can satisfy the desinged strength, bedded in cement mortar (1:3). | m² | 229.25 | Daily laborer | 230 | 26 | 747.5 | HCB 20 cm (pcs) | 2865.625 | 6.2421 | 17887.5284 | Stationary mixer 350 lit | 21 | 30 | 630 | 133.7577 | 30663.9454
[7 empty] | Mason | 115 | 52 | 747.5 | Cement (qtl) | 45.85 | 174.771 | 8013.2494 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant mason | 115 | 39 | 560.625 | Sand (m3) | 18.34 | 80 | 1467.2 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 1.68 | 5.41 | 9.0888 |  |  | 0 | 0 |  | 0
B | 2 | 1 | 2 | Ditto, but 100 mm thick. | m² | 54.53 | Daily laborer | 55 | 26 | 178.75 | HCB 10 cm (pcs) | 681.625 | 4.2421 | 2891.5239 | Stationary mixer 350 lit | 5 | 30 | 150 | 108.4156 | 5911.9019
[7 empty] | Mason | 28 | 52 | 182 | Cement (qtl) | 10.906 | 174.771 | 1906.0523 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant mason | 28 | 39 | 136.5 | Sand (m3) | 4.3624 | 80 | 348.992 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.4 | 5.41 | 2.164 |  |  | 0 | 0 |  | 0
B | 2 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 3 |  |  | ROOFING |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 3 | 1 | 1 | Roof cover in precoated or galvanized sheet metal USG 30 fixed to timber purlins. Price shall include G-30 flat sheet development length = 310 mm ridge cap and UV resistant washers. (Purlins measured separately and roof measured in horizontal projections) | m² | 223.26 | Carpenter | 38 | 52 | 247 | G-30 CIS (pcs) | 154.0494 | 85.4014 | 13156.0306 |  |  | 0 | 0 | 68.8701 | 15375.9309
[7 empty] | Assistant carpenter | 38 | 39 | 185.25 | Dome shaped nails (kg) | 40.1868 | 15.0803 | 606.028 |  |  | 0 | 0 |  | 0
[7 empty] | Daily laborer | 75 | 26 | 243.75 | Plastic washer (pcs) | 2902.38 | 0.05 | 145.119 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | G-30 sheet metal Ridge cover (m2) | 16.2667 | 30.2007 | 491.2645 |  |  | 0 | 0 |  | 0
B | 3 | 2 | 1 | Supply and fix G-30 galvanized flat metal sheet gutter as per the detail drawing. Price shall include all necessary accessories including metal bracket holders, one coat of anti rust and two coats of oil paint. Development length = 850 mm | m | 48.8 | Daily laborer | 17 | 26 | 55.25 | G-30 sheet metal Ridge cover (m2) | 48.8 | 30.2007 | 1473.7935 |  |  | 0 | 0 | 40.4342 | 1973.1865
[7 empty] | Solder | 17 | 52 | 110.5 | Screw (pcs) | 146.4 | 0.1 | 14.64 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fisher (pcs) | 146.4 | 0.1 | 14.64 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Soldering lead (kg) | 0.488 | 80.0803 | 39.0792 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fixing bracket for gutter and down pipes (pcs) | 98 | 1.5 | 147 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Antirust (gal) | 0.488 | 59.4511 | 29.0121 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.488 | 82.0111 | 40.0214 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 1.952 | 5.41 | 10.5603 |  |  | 0 | 0 |  | 0
B | 3 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 |  |  | CARPENTRY AND JOINERY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 1 |  | WOOD STRUCTURE |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 1 |  | Supply, fabricate and mount wood truss according to the structural drawing. Price shall include two coat of anti-termite treatment. and all other necessary accessories. The connection joints shall be approved by the responsible engineer. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 1 | 1 | Eucalyptus wood Horizontal truss members. Size dia.100 mm | m | 358.15 | Daily laborer | 90 | 26 | 292.5 | Eucalyptus Diam. 10 cm (ml) | 128 | 5.2421 | 670.9893 |  |  | 0 | 0 | 6.4674 | 2316.2877
[7 empty] | Carpenter | 90 | 52 | 585 | Nails (kg) | 17.5494 | 12.0803 | 212.001 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 90 | 39 | 438.75 | Mould Oil (lit) | 71.63 | 1 | 71.63 |  |  | 0 | 0 |  | 0
B | 4 | 1 | 2 | Eucalyptus wood vertical & diagonal truss members. Size dia.80 mm | m | 105.4 | Daily laborer | 27 | 26 | 87.75 | Eucalyptus diam 8 cm (ml) | 38 | 4.7421 | 180.1999 |  |  | 0 | 0 | 6.373 | 671.7156
[7 empty] | Carpenter | 27 | 52 | 175.5 | Nails (kg) | 5.1646 | 12.0803 | 62.3898 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 27 | 39 | 131.625 | Mould Oil (lit) | 21.08 | 1 | 21.08 |  |  | 0 | 0 |  | 0
B | 4 | 1 | 3 | Sawn zigba wood roof purlins placed at c/c 900 mm. Size 50 x 70 mm | m | 341.6 | Daily laborer | 86 | 26 | 279.5 | Sawn timber purlin 50 x 70 mm (ml) | 358.68 | 7 | 2510.76 |  |  | 0 | 0 | 12.0603 | 4119.8152
[7 empty] | Carpenter | 86 | 52 | 559 | Nails (kg) | 16.7384 | 12.0803 | 202.2045 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 86 | 39 | 419.25 | Mould Oil (lit) | 68.32 | 1 | 68.32 |  |  | 0 | 0 |  | 0
B | 4 | 2 |  | CEILINGS WORKS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 2 | 1 | Supply and fix 8 mm thick chip wood ceilings as per the engineers approval and according to the detail drawing. Price shall include 40 x 50 mm zigba wood battens with c/c spacing of 600 mm both ways, middle and corner strip and all other necessary accesso | m² | 135.3 | Daily laborer | 271 | 26 | 880.75 | Chip wood, thickness 8mm (m2) | 148.83 | 26.8507 | 3996.1878 |  |  | 0 | 0 | 81.8976 | 11080.7405
[7 empty] | Carpenter | 136 | 52 | 884 | Ceiling batten 4x5 cm (ml) | 487.08 | 4.1284 | 2010.8806 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 136 | 39 | 663 | Corner list (ml) | 541.2 | 3 | 1623.6 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 13.53 | 12.0803 | 163.4461 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Eucalyptus diam 8 cm (ml) | 135.3 | 4.7421 | 641.6066 |  |  | 0 | 0 |  | 0
B | 4 | 2 | 1 | 0.8 mm thick ribbed sheet metal soffit cover | m² | 26.32 | Daily laborer | 53 | 26 | 172.25 | 0.4 mm thick ribbed sheet metal (m2) | 28.952 | 95.6221 | 2768.45 |  |  | 0 | 0 | 154.4974 | 4066.371
[7 empty] | Carpenter | 27 | 52 | 175.5 | Ceiling batten 4x5 cm (ml) | 94.752 | 4.1284 | 391.1779 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 27 | 39 | 131.625 | Corner list (ml) | 105.28 | 3 | 315.84 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 2.632 | 12.0803 | 31.7953 |  |  | 0 | 0 |  | 0
B | 4 | 2 |  | FACIA BOARD |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 2 | 3 | Supply and fix Tid wood Facia board according to the detail drawing. Price shall include 3 coats of varnish paint. Size 20 x 250 mm. | ml | 68.2 | Daily laborer | 46 | 26 | 149.5 | Timber 2.5 cm thick (m3) | 0.682 | 4250 | 2898.5 |  |  | 0 | 0 | 51.5415 | 3515.1285
[7 empty] | Carpenter | 23 | 52 | 149.5 | Nails (kg) | 2.046 | 12.0803 | 24.7162 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 23 | 39 | 112.125 | Varnish (gal) | 1.364 | 82.0111 | 111.8631 |  |  | 0 | 0 |  | 0
B | 4 | 3 |  | Flush wooden door |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 3 |  | Supply, delivery and fix doors manufactured 4mm play wood and stifened properly, all as per the engineers approval, door schedule and detail drawing.The frames shall be designed and fixed to the plastering to allow the load on it. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 4 | 3 | 1 | Type D1: Size 900 x 2100 mm | No. | 3 | Daily laborer | 24 | 26 | 78 | Flush wooden door (m2) | 5.67 | 812.971 | 4609.5456 |  |  | 0 | 0 | 1662.8705 | 4988.6115
[7 empty] | Carpenter | 12 | 52 | 78 | Screw (pcs) | 18 | 0.1 | 1.8 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 12 | 39 | 58.5 | Fisher (pcs) | 18 | 0.1 | 1.8 |  |  | 0 | 0 |  | 0
[7 empty] | Painter | 12 | 39 | 58.5 | Varnish (gal) | 0.0567 | 82.0111 | 4.65 |  |  | 0 | 0 |  | 0
B | 5 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 5 |  |  | METAL WORKS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 5 |  |  | Supply, delivery and fix doors and windows manufactured from 28 x 1 mm LTZ profile, all as per the engineers approval and window door schedule and detail drawing.The frames shall be designed and fixed to the plastering to allow the load on the door. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 5 | 1 |  | DOORS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 5 | 1 | 1 | Type D1: Size 900 x 2100 mm | No. | 5 | Daily laborer | 40 | 26 | 130 | Metal door (m2) | 9.45 | 383.705 | 3626.0123 |  |  | 0 | 0 | 836.4776 | 4182.388
[7 empty] | Carpenter | 20 | 52 | 130 | Screw (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 20 | 39 | 97.5 | Fisher (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Painter | 20 | 39 | 97.5 | Antirust (gal) | 0.0945 | 59.4511 | 5.6181 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.0945 | 82.0111 | 7.75 |  |  | 0 | 0 |  | 0
B | 5 | 1 | 2 | Type D2: Size 700 x 2100 mm | No. | 5 | Daily laborer | 40 | 26 | 130 | Metal door (m2) | 1.47 | 383.705 | 564.0463 |  |  | 0 | 0 | 209.5337 | 1047.6684
[7 empty] | Carpenter | 20 | 52 | 130 | Screw (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 20 | 39 | 97.5 | Fisher (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Painter | 20 | 39 | 97.5 | Antirust (gal) | 0.0147 | 59.4511 | 0.87393 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.0147 | 82.0111 | 1.2056 |  |  | 0 | 0 |  | 0
B | 5 | 2 |  | WINDOWS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 5 | 2 | 1 | Type W1: 1000 x 1200 mm | No. | 5 | Daily laborer | 40 | 26 | 130 | Metal windows (m2) | 1.8 | 353.705 | 636.669 |  |  | 0 | 0 | 224.4439 | 1122.2196
[7 empty] | Carpenter | 20 | 52 | 130 | Screw (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 20 | 39 | 97.5 | Fisher (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Painter | 20 | 39 | 97.5 | Antirust (gal) | 0.018 | 59.4511 | 1.0701 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.018 | 82.0111 | 1.4762 |  |  | 0 | 0 |  | 0
B | 5 | 2 | 2 | Type W2: 1800 x 1200 mm | No. | 5 | Daily laborer | 40 | 26 | 130 | Metal windows (m2) | 1.74 | 353.705 | 615.4467 |  |  | 0 | 0 | 220.0973 | 1100.4863
[7 empty] | Carpenter | 20 | 52 | 130 | Screw (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant carpenter | 20 | 39 | 97.5 | Fisher (pcs) | 30 | 0.1 | 3 |  |  | 0 | 0 |  | 0
[7 empty] | Painter | 20 | 39 | 97.5 | Antirust (gal) | 0.0174 | 59.4511 | 1.0344 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.0174 | 82.0111 | 1.427 |  |  | 0 | 0 |  | 0
B | 5 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 |  |  | FINISHING WORKS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 1 |  | Apply three coats of plastering in cement mortar (1:3). |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 1 | 1 | To internal wall surface | m² | 324.03 | Daily laborer | 519 | 26 | 1686.75 | Cement (qtl) | 19.4418 | 174.771 | 3397.8624 | Stationary mixer 350 lit | 25.9224 | 30 | 777.672 | 24.7758 | 8028.1157
[7 empty] | Plasterer | 260 | 45.5 | 1478.75 | Sand (m3) | 6.4806 | 80 | 518.448 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 2.0738 | 5.41 | 11.2192 |  |  | 0 | 0 |  | 0
B | 6 | 1 | 2 | To external wall surface | m² | 191.37 | Daily laborer | 307 | 26 | 997.75 | Cement (qtl) | 11.4822 | 174.771 | 2006.7553 | Stationary mixer 350 lit | 15.3096 | 30 | 459.288 | 30.1275 | 5765.5039
[7 empty] | Plasterer | 154 | 45.5 | 875.875 | Sand (m3) | 3.8274 | 80 | 306.192 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 1.2248 | 5.41 | 6.626 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Eucalyptus diam 8 cm (ml) | 191.37 | 4.7421 | 907.4964 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Nails (kg) | 7.6548 | 12.0803 | 92.4721 |  |  | 0 | 0 |  | 0
B | 6 | 1 | 3 | Apply two coats of plastering in cement mortar (1:3) to recieve ceramic wall tile. Price shall include supply, pre-cleaning and preparation of the surface. | m² | 62.25 | Daily laborer | 100 | 26 | 325 | Cement (qtl) | 3.735 | 174.771 | 652.7696 | Stationary mixer 350 lit | 4.98 | 30 | 149.4 | 24.7962 | 1543.5659
[7 empty] | Plasterer | 50 | 45.5 | 284.375 | Sand (m3) | 1.245 | 80 | 99.6 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.3984 | 5.41 | 2.1553 |  |  | 0 | 0 |  | 0
B | 6 | 2 |  | Flooring |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 2 | 1 | 48 mm thick cement sand screed (1:3) to receive PVC floor tille | m² | 18 | Daily laborer | 29 | 26 | 94.25 | Cement (qtl) | 3.78 | 174.771 | 660.6343 | Stationary mixer 350 lit | 1.44 | 30 | 43.2 | 55.8065 | 1004.5164
[7 empty] | Plasterer | 15 | 45.5 | 85.3125 | Sand (m3) | 1.26 | 80 | 100.8 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.1152 | 5.41 | 0.62323 |  |  | 0 | 0 |  | 0
B | 6 | 2 | 2 | PVC floor tille, 2 mm thick | m² | 18 | Daily laborer | 9 | 26 | 29.25 | PVC tile (m2) | 18.36 | 48 | 881.28 |  |  | 0 | 0 | 63.4027 | 1141.2492
[7 empty] | Tiller | 9 | 65 | 73.125 | Adhesive (kg) | 2.7 | 50.0803 | 135.2167 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 2 | 3 | PVC skirting, 60 mm wide | m² | 54.6 | Daily laborer | 14 | 26 | 45.5 | PVC skirting (ml) | 55.692 | 10 | 556.92 |  |  | 0 | 0 | 13.8392 | 755.6219
[7 empty] | Tiller | 14 | 65 | 113.75 | CM-43 Glue (kg) | 0.819 | 30.0803 | 24.6357 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 2 | 4 | Terrazo floor tille, 20 mm thick. Price shall include supply, 30 mm cement screeding and other preparations | m² | 54 | Daily laborer | 37 | 26 | 120.25 | Cement (qtl) | 5.4 | 174.771 | 943.7633 | Stationary mixer 350 lit | 3.24 | 30 | 97.2 | 136.9169 | 7393.5138
[7 empty] | Tiller | 18 | 65 | 146.25 | Sand (m3) | 12.96 | 80 | 1036.8 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Terrazzo tile (m2) | 55.08 | 89.0138 | 4902.8773 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.2592 | 5.41 | 1.4023 |  |  | 0 | 0 |  | 0
B | 6 | 2 | 5 | Terrazo skirting stuck to wall, 100 mm wide. Price shall include supply, pre-cleaning and other preparation of the surface | m² | 85.8 | Daily laborer | 29 | 26 | 94.25 | Cement (qtl) | 0.858 | 174.771 | 149.9535 | Stationary mixer 350 lit | 2.574 | 30 | 77.22 | 27.8814 | 2392.2267
[7 empty] | Tiller | 15 | 65 | 121.875 | Sand (m3) | 0.858 | 80 | 68.64 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Terrazzo skirting (ml) | 87.516 | 20.9364 | 1832.2678 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.20592 | 5.41 | 1.114 |  |  | 0 | 0 |  | 0
B | 6 | 3 |  | Wall tille |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 3 | 1 | 6 mm thick white ceramic wall tile | m² | 62.25 | Daily laborer | 125 | 26 | 406.25 | Cement (qtl) | 0.6225 | 174.771 | 108.7949 |  |  | 0 | 0 | 115.3439 | 7180.1577
[7 empty] | Tiller | 63 | 65 | 511.875 | Sand (m3) | 0.6225 | 80 | 49.8 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Ceramic tile (m2) | 63.495 | 85.5619 | 5432.7544 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | White cement (Kg) | 87.15 | 6.0803 | 529.896 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 4 |  | PAVING |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 6 | 4 | 1 | 600 mm wide stone pavement around the building. Price shall include red ash or equivalent bedding material and half dia 400 mm concrete rain water pipe pointing as per the detail drawing and the engineers direction. | m² | 23.28 | Daily laborer | 16 | 26 | 52 | Cement (qtl) | 4.1904 | 174.771 | 732.3603 | Stationary mixer 350 lit | 0.4656 | 30 | 13.968 | 115.6639 | 2692.655
[7 empty] | Mason | 8 | 52 | 52 | Sand (m3) | 0.6984 | 80 | 55.872 |  |  | 0 | 0 |  | 0
[7 empty] | Assistant mason | 8 | 39 | 39 | Fuel (lit) | 0.037248 | 5.41 | 0.20151 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Half concrete pipe diam 400 mm (ml) | 25 | 35 | 875 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Tracheatic stone (m3) | 7.6824 | 80 | 614.592 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Red ash (m3) | 2.5608 | 80 | 204.864 |  |  | 0 | 0 |  | 0
B | 6 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 7 |  |  | GLAZING |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 7 | 1 | 1 | Supply and fix 4 mm thick clear sheet glass to metal beads and puttied with approved quality of putty. | m² | 10.26 | Daily laborer | 6 | 26 | 19.5 | 4 mm thick clear glass (m2) | 11.286 | 52.9814 | 597.9481 |  |  | 0 | 0 | 65.4848 | 671.8744
[7 empty] | Glazer | 3 | 52 | 19.5 | Putty glass (kg) | 4.104 | 5.3003 | 21.7523 |  |  | 0 | 0 |  | 0
B | 7 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 8 |  |  | PAINTING |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 8 | 1 |  | Provide and apply three coats emulsion paint All required materials as per approval of the engineer. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 8 | 1 | 1 | to internal wall surfaces flushed finished | m² | 324.03 | Daily laborer | 107 | 26 | 347.75 | Plastic paint (gal) | 22.6821 | 51.5511 | 1169.2872 |  |  | 0 | 0 | 8.1442 | 2638.9611
[7 empty] | Painter | 107 | 39 | 521.625 | Stucco (kg) | 129.612 | 4.0803 | 528.8526 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Glue for stucco (animal glue) (kg) | 3.2403 | 6.0803 | 19.7019 |  |  | 0 | 0 |  | 0
B | 8 | 1 | 2 | to external plastered wall surfaces. | m² | 191.37 | Daily laborer | 64 | 26 | 208 | Plastic paint (gal) | 13.3959 | 51.5511 | 690.5734 |  |  | 0 | 0 | 8.1791 | 1565.237
[7 empty] | Painter | 64 | 39 | 312 | Stucco (kg) | 76.548 | 4.0803 | 312.3369 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Glue for stucco (animal glue) (kg) | 1.9137 | 6.0803 | 11.6358 |  |  | 0 | 0 |  | 0
B | 8 | 1 | 3 | to chip wooden ceiling | m² | 135.3 | Daily laborer | 45 | 26 | 146.25 | Plastic paint (gal) | 9.471 | 51.5511 | 488.2405 |  |  | 0 | 0 | 8.1639 | 1104.5749
[7 empty] | Painter | 45 | 39 | 219.375 | Stucco (kg) | 54.12 | 4.0803 | 220.8245 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Glue for stucco (animal glue) (kg) | 1.353 | 6.0803 | 8.2266 |  |  | 0 | 0 |  | 0
B | 8 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 |  |  | SANITARY INSTALLATION |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 |  |  | SANITARY EQUIPMENT (FIXTURES) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 1 | 1 | Supply and fix Awassa ceramics hand wash basins made of white vitreous china, with chrome plated cold and hot water mixer, complete with plug, chrome plated chain holder, P-smell trap with connection pipe and with all other necessary accessories. | No. | 2 | Plumber | 1 | 52 | 6.5 | Tabor HWB, size 50 x 40 cm complete with faucets, smell trap and plug (pcs) | 2 | 603.705 | 1207.41 |  |  | 0 | 0 | 712.5516 | 1425.1032
[7 empty] | Daily laborer | 1 | 26 | 3.25 | Flexible pipe diam 15 mm (pcs) | 4 | 15 | 60 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | HWB fixing support (pcs) | 4 | 30 | 120 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Rubber plug diam. 50 mm (pcs) | 2 | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 1 | 2 | Supply and fix Awassa ceramics wash down water closets made of white vitreous china with plastic seat and cover including low flush cistern. Complete with all necessary accessories | No. | 2 | Plumber | 1 | 52 | 6.5 | Tabor WC complete with plastic seats, cover and low flush cistern (pcs) | 2 | 906.175 | 1812.35 |  |  | 0 | 0 | 944.571 | 1889.142
[7 empty] | Daily laborer | 1 | 26 | 3.25 | Flexible pipe diam 15 mm (pcs) | 2 | 15 | 30 |  |  | 0 | 0 |  | 0
B | 9 | 1 | 3 | Supply and fix Awassa ceramics toilet paper holder with chrome plated brass wall flanged roll with chrome plated fastening screws and other accessories. | No. | 2 |  |  | 0 | 0 | Tabor toilet paper holder 150 x 150 mm (pcs) | 2 | 35 | 70 |  |  | 0 | 0 | 35.7 | 71.4
B | 9 | 1 | 4 | Supply and fix soap holder out of Awassa ceramic or equivalent, fixed with chrome plated brass wall flanged roll chrome plated fastening screws and other accessories. Size: 305 x 150 mm | No. | 4 |  |  | 0 | 0 | Tabor soap holder 150 x 150 mm (pcs) | 4 | 35 | 140 |  |  | 0 | 0 | 35.7 | 142.8
B | 9 | 1 | 5 | Supply and fix Enameled cast iron shower unit, with chrome plated valves and shower head and other accessories. Size: 700x700 mm | No. | 2 | Plumber | 1 | 52 | 6.5 | Shower try (Enameled cast Iron, complete with all accessories and head, 700mm x 700 mm) (pcs) | 2 | 600 | 1200 |  |  | 0 | 0 | 688.3725 | 1376.745
[7 empty] | Daily laborer | 1 | 26 | 3.25 | Chrome plated gate valve | 2 | 70 | 140 |  |  | 0 | 0 |  | 0
B | 9 | 1 | 6 | Supply and fix Kitchen double boul sink out of stainless steel, with chrome plated Mixing tape, complete with plug, chrome plated chain holder and other accessories. Size: 1200x500 mm | No. | 2 | Plumber | 1 | 52 | 6.5 | Kitchen sink (stainless steel, 1200mm x 500 mm) (pcs) | 2 | 1301.976 | 2603.952 |  |  | 0 | 0 | 1363.588 | 2727.176
[7 empty] | Daily laborer | 1 | 26 | 3.25 | Flexible pipe diam 15 mm (pcs) | 4 | 15 | 60 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Rubber plug diam. 50 mm (pcs) | 2 | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 1 | 5 | Supply and fix floor drains made of polished steel of approved quality, complete with P-smell trap and all other necessary fittings and accessories. Size: - Dia. 50 mm | No. | 2 |  |  | 0 | 0 | Steel floor drain diam. 50 mm (pcs) | 2 | 30 | 60 |  |  | 0 | 0 | 30.6 | 61.2
B | 9 | 1 | 6 | Supply and fix glass mirror complete with chrome plated brass frames and screws and all necessary accessories. Price shall include all civil works. Size: 500 x 400 mm | No. | 2 | Plumber | 1 | 52 | 6.5 | Glass mirror complete with fixing screws, size 500 x 400 mm (pcs) | 2 | 120.988 | 241.976 | Electrical drilling machine | 1 | 1 | 1 | 128.8903 | 257.7805
[7 empty] | Daily laborer | 1 | 26 | 3.25 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 2 |  | WATER SUPPLY PIPES AND VALVES |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 2 |  | Water pipes shall be galvanized steel and be fixed to, walls, beams or etc. Unit price shall include all assistance civil works and necessary fittings such as T- bends and Y- reducers. Gate valves and other necessary valves shall be fixed properly as per |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 2 |  | Supply and install galvanized steel pipes to internal water distribution system as shown on the drawing complete with all the necessary accessories. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 2 | 1 | Dia. 15 mm | m | 12 | Plumber | 3 | 52 | 19.5 | GS Pipe diam 15 mm (pcs) | 2 | 70.39 | 140.78 |  |  | 0 | 0 | 23.593 | 283.1158
[7 empty] | Daily laborer | 3 | 26 | 9.75 | GS Elbow diam 15 mm (pcs) | 34 | 2 | 68 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | GS Tee diam 15 mm (pcs) | 9 | 2 | 18 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Hemp (kg) | 0.43 | 50.0803 | 21.5345 |  |  | 0 | 0 |  | 0
B | 9 | 3 |  | VALVES |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 3 |  | Supply and fix approved quality brass gate valves at internal branch water pipes and pipe inlet to building of the following sizes and as where shown on the drawing. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 3 | 1 | Dia. 15 mm | No. | 4 |  |  | 0 | 0 | Brass gate valve diam. 15 mm (pcs) | 4 | 66.97 | 267.88 |  |  | 0 | 0 | 71.3694 | 285.4776
[9 empty] | 0 | 0 | GS Union diam. 15 mm (pcs) | 4 | 3 | 12 |  |  | 0 | 0 |  | 0
B | 9 | 4 |  | WASTE, VENT AND RAIN WATER PIPES AND ACCESSORIES |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 4 |  | All domestic waste, vent and storm water pipe lines shall be PVC pipes and provided with a minimum slope of 2% towards the outlet. All PVC pipes and necessary fittings shall be standard quality and be free from damage during storage, construction and etc. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 4 |  | Supply and lay internal PVC waste and vent pipes according to where shown on the drawings. Complete with all the necessary fittings. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 4 | 1 | Dia. 50 mm | m | 7 | Plumber | 4 | 52 | 26 | PVC pipe diam. 50 mm (ml) | 7.35 | 5.83 | 42.8505 |  |  | 0 | 0 | 31.202 | 218.4139
[7 empty] | Daily laborer | 7 | 26 | 22.75 | PVC elbow diam. 50 mm (pcs) | 8 | 7 | 56 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | PVC reducer diam. 110/50 mm (pcs) | 2 | 20 | 40 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | CM-43 glue (kg) | 0.882 | 30.0803 | 26.5308 |  |  | 0 | 0 |  | 0
B | 9 | 4 | 2 | Dia. 110 mm | m | 3.5 | Plumber | 2 | 52 | 13 | PVC pipe diam. 110 mm (ml) | 3.675 | 18.83 | 69.2002 |  |  | 0 | 0 | 78.2386 | 273.835
[7 empty] | Daily laborer | 4 | 26 | 13 | PVC tee diam. 110 mm (pcs) | 4 | 40 | 160 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | CM-43 glue (kg) | 0.441 | 30.0803 | 13.2654 |  |  | 0 | 0 |  | 0
B | 9 | 5 |  | Supply and lay approved quality storm water galvanized sheet metal down pipes according to where shown on the drawing. Price shall include all the necessary connecting pieces. |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 9 | 5 | 1 | Dia. 100 x 80 mm | m | 24 | Daily laborer | 8 | 26 | 26 | G-30 sheet metal Ridge cover (m2) | 12 | 30.2007 | 362.4083 |  |  | 0 | 0 | 25.6988 | 616.772
[7 empty] | Solder | 8 | 52 | 52 | Screw (pcs) | 25.2 | 0.1 | 2.52 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fisher (pcs) | 25.2 | 0.1 | 2.52 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Soldering lead (kg) | 0.24 | 80.0803 | 19.2193 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fixing bracket for gutter and down pipes (pcs) | 48 | 1.5 | 72 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Antirust (gal) | 0.48 | 59.4511 | 28.5365 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Synthetic paint (gal) | 0.48 | 82.0111 | 39.3653 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.02016 | 5.41 | 0.10907 |  |  | 0 | 0 |  | 0
B | 9 | 6 | 1 | Manhole out of internally plastered stone masonry/ HCB wall with 80 mm thick mass concrete base slab and 80 mm RC over. Price shall include all required works. Size: 600 x 600 x 700 mm inner diameter | No. | 3 | Daily laborer | 96 | 26 | 312 | Basaltic stone (m3) | 6.468 | 80 | 517.44 | stationary mixer 350 lit | 0.99 | 30 | 29.7 | 776.5794 | 2329.7383
[7 empty] | Mason | 48 | 52 | 312 | Sand (m3) | 1.0853 | 80 | 86.8271 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Cement (qtl) | 5.1683 | 174.771 | 903.2654 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Crushed aggregate, 20 mm (m3) | 0.16848 | 262.385 | 44.2066 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Fuel (lit) | 0.0792 | 5.41 | 0.42847 |  |  | 0 | 0 |  | 0
[9 empty] | 0 | 0 | Rebar diam 8 mm (kg) | 7.5 | 10.4253 | 78.1896 |  |  | 0 | 0 |  | 0
B | 9 |  |  | TOTAL CARRIED TO SUMMARY |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 |  |  | ELLECTRICAL INSTALLATION WORKS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 1 |  | SUPPLY AND INSTALL |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 3 |  | CONDUITS AND PIPES |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 3 | 1 | Supply and install PVC pipe of 36 mm diameter | m | 90 | Electrician | 15 | 52 | 97.5 | Condute diam 16 mm (pcs) | 33 | 5.64 | 186.12 |  |  | 0 | 0 | 22.8776 | 2058.9872
[7 empty] | Daily laborer | 15 | 26 | 48.75 | PVC Clamps diam 16 mm (pcs) | 270 | 3 | 810 |  |  | 0 | 0
[9 empty] | 0 | 0 | 2.5 mm2 wire (ml) | 360 | 2.434 | 876.245 |  |  | 0 | 0
B | 10 | 4 |  | DISTRIBUTION BOARDS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 4 | 1 | Flush mounting distribution board MDB1, in sheet steel enclosure with lockable door and with phase, neutral, earth bus-bars of 63A/3P and consisting of:- 1 pc main ACB of 63A/3P 1 pc ACB of 32A/3P 13 pcs ACB of 16A/1P 1 pc ACB of 10A/1P 25% reserve p | No. | 1 |  |  | 0 | 0 | Surface mounting distribution board MDB1, in sheet steel enclosure with lockable door and with phase, neutral, earth bus-bars of 63A/3P and consisting of:- 1 pc ACB of 32A/3P 4 pcs ACB of 16A/1P 1 pc ACB of 10A/1P | 1 | 502.47 | 502.47 |  |  | 0 | 0 | 512.5194 | 512.5194
[9 empty] | 0 |  |  |  | 0
B | 10 | 5 |  | LIGHT POINTS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 5 | 1 | Supply and install flush mounted light points fed through PVC insulated conductors of 3 x 2.5 mm² inside PVC conduits of 16 mm diameter, including junction boxes with covers insulating screw cap connectors. | No. | 15 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
B | 10 | 6 |  | Switches |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 6 | 1 | Flush mounting single switch, 7740 01 + 774041 | No. | 10 | Electrician | 5 | 52 | 32.5 | Junction box diam 65 mm | 30 | 0.85 | 25.5 |  |  | 0 | 0 | 48.3225 | 483.225
[7 empty] | Daily laborer | 5 | 26 | 16.25 | Connectors diam 5mm (pcs) | 90 | 0.55 | 49.5 |  |  | 0 | 0
[9 empty] | 0 | 0 | Single switch (pcs) | 10 | 35 | 350 |  |  | 0 | 0
B | 10 | 6 | 3 | Flush mounting two-way switch, 7740 06 + 774041 | No. | 10 | Electrician | 5 | 52 | 32.5 | Junction box diam 65 mm | 30 | 0.85 | 25.5 |  |  | 0 | 0 | 63.6225 | 636.225
[7 empty] | Daily laborer | 5 | 26 | 16.25 | Connectors diam 5mm (pcs) | 90 | 0.55 | 49.5 |  |  | 0 | 0
[9 empty] | 0 | 0 | Two-way switches (pcs) | 10 | 50 | 500 |  |  | 0 | 0
B | 10 | 7 |  | SOCKET OUTLET POINTS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 7 | 1 | Supply and install 10-16A/1P socket outlet points fed through PVC insulated conductors of 3 x 2.5 mm² inside PVC conduits of 16 mm diameter including junction boxes with covers, and insulating screw cap connectors all for flush mounting. | No. | 10 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
B | 10 | 7 |  | SOCKET OUTLETS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 7 |  | Supply and install socket Outlets (Type Legrand Suno or Equivalent) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 7 | 1 | Flush mounting socket outlet of 10A/1P, 774020+774041 | No. | 10 | Electrician | 5 | 52 | 32.5 | Junction box diam 65 mm | 30 | 0.85 | 25.5 |  |  | 0 | 0 | 48.3225 | 483.225
[7 empty] | Daily laborer | 5 | 26 | 16.25 | Socket (pcs) | 10 | 35 | 350 |  |  | 0 | 0
[9 empty] | 0 | 0 | Connectors diam 5mm (pcs) | 90 | 0.55 | 49.5 |  |  | 0 | 0
B | 10 | 8 |  | LIGHT FITTINGS AND LAMPS |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 8 |  | Supply and install Light Fittings and Lamps (Specified Type or Equivalent) |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
B | 10 | 8 | 1 | Fluorescent fitting type PhilipsTMS 022/136 I +2 x TLD 36W/840 lamps | No. | 5 | Electrician | 3 | 52 | 19.5 | Junction box diam 65 mm | 5 | 0.85 | 4.25 |  |  | 0 | 0 | 465.834 | 2329.17
[7 empty] | Daily laborer | 3 | 26 | 9.75 | Fluorescent lamp with holders and balustrade TMW 012/236w (pcs) | 5 | 450 | 2250 |  |  | 0 | 0
B | 10 | 8 | 2 | Incandescent fitting type RZB 22147.912 + TC 9W lamp | No. | 10 | Electrician | 5 | 52 | 32.5 | Junction box diam 65 mm | 10 | 0.85 | 8.5 |  |  | 0 | 0 | 413.8395 | 4138.395
[7 empty] | Daily laborer | 5 | 26 | 16.25 | E-27 type Incandescent Lamps with holder (pcs) | 10 | 400 | 4000 |  |  | 0 | 0
B | 10 |  |  | TOTAL CARRIED TO SUMMARY
244991.446

## Resource sheet and cost summary
RESOURCE REQUIREMENT SHEET
Project: Residence 1
LABOUR
| S/No. | TRADE | Labour wage per hr | Labor wage per day |  | LABOUR HOURS | Total Amount
| 1 | Assistant bar-bender | 4.875 | 39 |  | 18 | 87.75
| 2 | Assistant carpenter | 4.875 | 39 |  | 569 | 2773.875
| 3 | Assistant mason | 4.875 | 39 |  | 397 | 1935.375
| 4 | Bar-bender | 6.5 | 52 |  | 18 | 117
| 5 | Carpenter | 6.5 | 52 |  | 569 | 3698.5
| 6 | Daily laborer | 3.25 | 26 |  | 5244 | 17043
| 7 | Glazer | 6.5 | 52 |  | 3 | 19.5
| 8 | Gang leader | 4.875 | 39 |  | 79 | 385.125
| 9 | Mason | 6.5 | 52 |  | 534 | 3471
| 10 | Painter | 4.875 | 39 |  | 296 | 1443
| 11 | Plasterer | 5.6875 | 45.5 |  | 479 | 2724.3125
| 12 | Plumber | 6.5 | 52 |  | 14 | 91
| 13 | SE Operator | 4.875 | 39 |  | 39 | 190.125
| 14 | Solder | 6.5 | 52 |  | 25 | 162.5
| 15 | Tiller | 8.125 | 65 |  | 119 | 966.875
| 16 | Electrician | 6.5 | 52 |  | 38 | 247
MATERIAL
S/No. |  | TYPE | UNIT MEASURE | Unit rate |  | QUANTITY | Total amount
HOP | 1 | 0.4 mm thick ribbed sheet metal (m2) | M2 | 95.6221 |  | 28.952 | 2768.45
HOP | 2 | 2.5 mm2 wire (ml) | ml | 2.434 |  | 360 | 876.245
HOP | 3 | 4 mm thick clear glass (m2) | M2 | 52.9814 |  | 11.286 | 597.9481
HOP | 4 | Adhesive (kg) | kg | 50.0803 |  | 2.7 | 135.2167
HOP | 5 | Antirust (gal) | Gal | 59.4511 |  | 1.1126 | 66.1453
HOP | 6 | black steel wire diam 1.5 mm (KG) | Kg | 12.0803 |  | 15.2616 | 184.3649
HOP | 7 | Brass gate valve diam. 15 mm (pcs) | Pcs | 66.97 |  | 4 | 267.88
HOP | 8 | Ceiling batten 4x5 cm (ml) | ml | 4.1284 |  | 581.832 | 2402.0585
HOP | 9 | Cement (qtl) | Qtl | 174.771 |  | 290.2622 | 50729.4052
HOP | 10 | Ceramic tile (m2) | m2 | 85.5619 |  | 63.495 | 5432.7544
HOP | 11 | Chip wood, thickness 8mm (m2) | m2 | 26.8507 |  | 148.83 | 3996.1878
HOP | 12 | CM-43 glue (kg) | Kg | 30.0803 |  | 2.142 | 64.4319
HOP | 13 | Corner list (ml) | ml | 3 |  | 646.48 | 1939.44
HOP | 14 | Condute diam 16 mm (pcs) | Pcs | 5.64 |  | 33 | 186.12
HOP | 15 | Connectors diam 5mm (pcs) | Pcs | 0.55 |  | 270 | 148.5
HOP | 16 | Chrome plated gate valve | Pcs | 70 |  | 2 | 140
HOP | 17 | Dome shaped nails (kg) | Kg | 15.0803 |  | 40.1868 | 606.028
HOP | 18 | E-27 type Incandescent Lamps with holder (pcs) | Pcs | 400 |  | 10 | 4000
HOP | 19 | hEMP (kg) | Kg | 50.0803 |  | 0.43 | 21.5345
HOP | 20 | Fisher (pcs) | Pcs | 0.1 |  | 291.6 | 29.16
HOP | 21 | Fixing bracket for gutter and down pipes (pcs) | Pcs | 1.5 |  | 146 | 219
HOP | 22 | Flexible pipe diam 15 mm (pcs) | Pcs | 15 |  | 12 | 180
HOP | 23 | Fluorescent lamp with holders and balustrade TMW 012/236w (pcs) | Pcs | 450 |  | 5 | 2250
HOP | 24 | Flush wooden door (m2) | m2 | 812.971 |  | 0 | 0
HOP | 25 | G-30 CIS (pcs) | Pcs | 85.4014 |  | 154.0494 | 13156.0306
HOP | 26 | G-30 sheet metal Ridge cover (m2) | m2 | 30.2007 |  | 77.0667 | 2327.4663
HOP | 27 | Glass mirror complete with fixing screws, size 500 x 400 mm (pcs) | Pcs | 120.988 |  | 2 | 241.976
HOP | 28 | Glue for stucco (animal glue) (kg) | Kg | 6.0803 |  | 6.507 | 39.5643
HOP | 29 | GS Elbow diam 15 mm (pcs) | Pcs | 2 |  | 34 | 68
HOP | 30 | GS Pipe diam 15 mm (pcs) | Pcs | 70.39 |  | 2 | 140.78
HOP | 31 | GS Tee diam 15 mm (pcs) | Pcs | 2 |  | 9 | 18
HOP | 32 | GS Union diam. 15 mm (pcs) | Pcs | 3 |  | 4 | 12
HOP | 33 | HWB fixing support (pcs) | Pcs | 30 |  | 4 | 120
HOP | 34 | Junction box diam 65 mm | Pcs | 0.85 |  | 105 | 89.25
HOP | 35 | Kitchen sink (stainless steel, 1200mm x 500 mm) (pcs) | Pcs | 1301.976 |  | 2 | 2603.952
HOP | 36 | Metal door (m2) | m2 | 383.705 |  | 10.92 | 4190.0586
HOP | 37 | Metal windows (m2) | m2 | 353.705 |  | 3.54 | 1252.1157
HOP | 38 | Nails (kg) | Kg | 12.0803 |  | 101.9872 | 1232.0328
HOP | 39 | Panel (m2hrs) | m2hrs | 0.1 |  | 977.92 | 97.792
HOP | 40 | Plastic paint (gal) | gal | 51.5511 |  | 45.549 | 2348.1011
HOP | 41 | Plastic washer (pcs) | Pcs | 0.05 |  | 2902.38 | 145.119
HOP | 42 | Putty glass (kg) | Kg | 5.3003 |  | 4.104 | 21.7523
HOP | 43 | PVC Clamps diam 16 mm (pcs) | Pcs | 3 |  | 270 | 810
HOP | 44 | PVC elbow diam. 50 mm (pcs) | Pcs | 7 |  | 8 | 56
HOP | 45 | PVC pipe diam. 110 mm (ml) | ml | 18.83 |  | 3.675 | 69.2002
HOP | 46 | PVC pipe diam. 50 mm (ml) | ml | 5.83 |  | 7.35 | 42.8505
HOP | 47 | PVC reducer diam. 110/50 mm (pcs) | Pcs | 20 |  | 2 | 40
HOP | 48 | PVC skirting (ml) | ml | 10 |  | 55.692 | 556.92
HOP | 49 | PVC tee diam. 110 mm (pcs) | Pcs | 40 |  | 4 | 160
HOP | 50 | PVC tile (m2) | m2 | 48 |  | 18.36 | 881.28
HOP | 51 | Rebar diam 10 mm (kg) | Kg | 10.4253 |  | 0 | 0
HOP | 52 | Rebar diam 12 mm (kg) | Kg | 10.4253 |  | 379.8757 | 3960.3091
HOP | 53 | Rebar diam 6 mm (kg) | Kg | 10.4253 |  | 0 | 0
HOP | 54 | Rebar diam 8 mm (kg) | Kg | 10.4253 |  | 405.9681 | 4232.3291
HOP | 55 | Rubber plug diam. 50 mm (pcs) | Pcs | 0 |  | 4 | 0
HOP | 56 | Sawn timber purlin 50 x 70 mm (ml) | ml | 7 |  | 358.68 | 2510.76
HOP | 57 | Screw (pcs) | Pcs | 0.1 |  | 291.6 | 29.16
HOP | 58 | Shower try (Enameled cast Iron, complete with all accessories and head, 700mm x 700 mm) (pcs) | Pcs | 600 |  | 2 | 1200
HOP | 59 | Single switch (pcs) | Pcs | 35 |  | 10 | 350
HOP | 60 | Socket (pcs) | Pcs | 35 |  | 10 | 350
HOP | 61 | Soldering lead (kg) | kg | 80.0803 |  | 0.728 | 58.2984
HOP | 62 | Steel floor drain diam. 50 mm (pcs) | Pcs | 30 |  | 2 | 60
HOP | 63 | Stucco (kg) | Kg | 4.0803 |  | 260.28 | 1062.014
HOP | 64 | Surface mounting distribution board MDB1, | Pcs | 502.47 |  | 1 | 502.47
HOP | 65 | Synthetic paint (gal) | gal | 82.0111 |  | 1.1126 | 91.2455
HOP | 66 | Tabor HWB, size 50 x 40 cm complete with faucets, smell trap and plug (pcs) | Pcs | 603.705 |  | 2 | 1207.41
HOP | 67 | Tabor soap holder 150 x 150 mm (pcs) | Pcs | 35 |  | 4 | 140
HOP | 68 | Tabor toilet paper holder 150 x 150 mm (pcs) | Pcs | 35 |  | 2 | 70
HOP | 69 | Tabor WC complete with plastic seats, cover and low flush cistern (pcs) | Pcs | 906.175 |  | 2 | 1812.35
HOP | 70 | Terrazzo skirting (ml) | ml | 20.9364 |  | 87.516 | 1832.2678
HOP | 71 | Terrazzo tile (m2) | m2 | 89.0138 |  | 55.08 | 4902.8773
HOP | 72 | Timber 2.5 cm thick (m3) | m3 | 4250 |  | 1.8012 | 7655.1
HOP | 73 | Two-way switches (pcs) | Pcs | 50 |  | 10 | 500
HOP | 74 | Varnish (Gal) | gal | 82.0111 |  | 1.364 | 111.8631
HOP | 75 | White cement (Kg) | Kg | 6.0803 |  | 87.15 | 529.896
LP | 1 | Crushed aggregate, 20 mm (m3) | m3 | 262.385 |  | 24.6267 | 6461.6714
LP | 2 | Basaltic stone (m3) | m3 | 80 |  | 52.0695 | 4165.56
LP | 3 | Eucalyptus diam 8 cm (ml) | Pcs | 4.7421 |  | 496.1048 | 2352.5804
LP | 4 | Eucalyptus Diam. 10 cm (ml) | Pcs | 5.2421 |  | 600.768 | 3149.2882
LP | 5 | Fuel (lit) | lit | 5.41 |  | 31.3795 | 169.763
LP | 6 | Half concrete pipe diam 400 mm (ml) | Pcs | 35 |  | 25 | 875
LP | 7 | HCB 10 cm (pcs) | Pcs | 4.2421 |  | 681.625 | 2891.5239
LP | 8 | HCB 20 cm (pcs) | Pcs | 6.2421 |  | 2865.625 | 17887.5284
LP | 9 | Mould Oil (lit) | lit | 1 |  | 168.3644 | 168.3644
LP | 10 | Red ash (m3) | m3 | 80 |  | 2.5608 | 204.864
LP | 11 | Sand (m3) | m3 | 80 |  | 88.2928 | 7063.4271
LP | 12 | Tracheatic stone (m3) | m3 | 80 |  | 92.1624 | 7372.992
Legend
| HOP | Head office purchase
| LP | Local purchase
EQUIPMENT
| S/No. | TYPE | Hourly rate |  | MACHINE HOUR | Total amount
| 1 | Electrical drilling machine | 1 |  | 1 | 1
| 2 | Plate compactor | 7 |  | 20.848 | 145.936
| 3 | Stationary mixer 350 lit | 30 |  | 157.9216 | 4737.648
| 4 | Vibrator | 7 |  | 141 | 987
|  | Small tools and equipment |  |  | 824.5504

## Rough schedule
Targets
1 | Project start time | 2008-01-01
2 | Project Duration | 120 | calendar days
3 | Project finish date | 2008-04-30
4 | Working days per week | 6 days
5 | Planning unit | Days
ID No | Task | Unit | Qty | Duration | Predecessor | Responsibility | Area | Remark
| Site handover |  |  |  |  | Project manager | own force
1 | Site clearing | m² | 250.74 | 2 |  | forman 1 | own force | EEPCO should remove the pole before site clearing work is started
2 | Trench excavation | m³ | 54.15 | 3 | 1 | forman 1 | own force
3 | Backfill under hard core | m³ | 26.06 | 3 | 13 | forman 1 | own force
4 | 250 mm thick basaltic stone hardcore | m² | 130.29 | 4 | 3 | forman 1 | own force
5 | Lean concrete Under masonry | m² | 27.06 | 1 | 2 | subcontractor 1 | sub contract | Due to cement delivery time, start not earlier than October 10,2007
6 | C-25 concrete In grade beams | m³ | 5.69 | 1 | 8 | subcontractor 1 | sub contract
7 | C-25 concrete In 100 mm thick floor slab | m² | 161.68 | 2 | 4,9 | subcontractor 1 | sub contract
8 | Form work To grade beams, errection | m² | 55.96 | 3 | 13 | forman 1 | own force
9 | Form work To grade beams, dismantling | m² | 55.96 | 1 | 6 | forman 1 | own force
10 | Dia 8 mm deformed bar | kg | 312.9585 | 7 |  | subcontractor 2 | sub contract
11 | Dia 12 mm deformed bar | kg | 155.4 | 7 |  | subcontractor 2 | sub contract
12 | 400 mm thick basaltic stone masonry, below ground surface. | m³ | 54.15 | 10 | 5 | forman 1 | own force
13 | 400 mm thick basaltic stone masonry, above ground surface. | m³ | 16.25 | 4 | 12 | forman 1 | own force
14 | C-25 In elevation columns | m³ | 1.98 | 1 | 16 | subcontractor 1 | sub contract
15 | C-25 In roof beams | m³ | 4.54 | 1 | 17 | subcontractor 1 | sub contract
16 | Form work For elevation columns | m² | 10.32 | 1 | 7 | forman 1 | own force
17 | Form work For roof beams, errection | m² | 55.96 | 7 | 14 | forman 1 | own force
18 | Form work For roof beams, dismantling | m² | 56.96 | 1 | 15 | forman 1 | own force
19 | Dia 8 mm deformed bar | kg | 77.6965 | 15 |  | subcontractor 2 | sub contract
20 | Dia 12 mm deformed bar | kg | 217.0272 | 15 |  | subcontractor 2 | sub contract
21 | Class C, 200 mm thick HCB wall | m² | 229.25 | 21 | 18 | forman 1 | own force
22 | Class C, 100 mm thick HCB wall | m² | 54.53 | 21 | 21 | forman 1 | own force
23 | Roof cover, USG 30 | m² | 223.26 | 4 | 27 | forman 1 | own force
24 | G-30 galvanized flat metal sheet gutter | m | 48.8 | 2 | 23,30 | forman 1 | own force
25 | Eucalyptus wood Horizontal truss members. Size dia.100 mm | m | 358.15 | 7 | 15 | forman 1 | own force
26 | Eucalyptus wood vertical & diagonal truss members. Size dia.80 mm | m | 105.4 | 7 | 15 | forman 1 | own force
27 | Sawn zigba wood roof purlins placed at c/c 900 mm. Size 50 x 70 mm | m | 341.6 | 3 | 25,26 | forman 1 | own force
28 | 8 mm thick chip wood ceilings | m² | 135.3 | 4 | 36 | forman 1 | own force
29 | 0.8 mm thick ribbed sheet metal soffit cover | m² | 26.32 | 1 | 37 | forman 1 | own force
30 | Tid wood Facia board | m | 68.2 | 1 | 37 | forman 1 | own force
31 | FD Type D1: Size 900 x 2100 mm | No. | 3 | 2 | 36,39 | forman 1 | own force
32 | MD Type D1: Size 900 x 2100 mm | No. | 5 | 2 | 37 | forman 1 | own force
33 | MD Type D2: Size 700 x 2100 mm | No. | 5 | 2 | 32 | forman 1 | own force
34 | MW Type W1: 1000 x 1200 mm | No. | 5 | 2 | 32 | forman 1 | own force
35 | MW Type W2: 1800 x 1200 mm | No. | 5 | 2 | 32 | forman 1 | own force
36 | 3 coats of Plaster To internal wall surface | m² | 324.03 | 15 | 21,22 | forman 1 | own force
37 | 3 coats of Plaster To external wall surface | m² | 191.37 | 15 | 21,22 | forman 1 | own force
38 | Two coats of plastering | m² | 62.25 | 15 | 21,22 | forman 1 | own force
39 | 48 mm thick trowel finished cement sand screed (1:3) to receive PVC tile | m² | 18 | 3 | 36 | forman 1 | own force
40 | PVC floor tile, 2 mm thick | m² | 18 | 1 | 39,47,48,49 | forman 1 | own force
41 | PVC skirting, 60 mm wide | m² | 54.6 | 1 | 40 | forman 1 | own force
42 | Terrazzo floor tile, 20 mm thick. | m² | 54 | 3 | 39 | forman 1 | own force
43 | Terrazzo skirting stuck to wall, 100 mm wide. | m² | 85.8 | 3 | 42 | forman 1 | own force
44 | 6 mm thick white ceramic wall tile | m² | 62.25 | 2 | 38 | forman 1 | own force
45 | 600 mm wide stone pavement around the building. | m² | 23.28 | 2 | 37 | forman 1 | own force
46 | 4 mm thick clear glass |  | 10.26 | 1 | 47,48,49 | forman 1 | own force
47 | Plastic paint to internal wall surfaces flushed finished | m² | 324.03 | 15 | 36 | forman 1 | own force
48 | Plastic paint to external plastered wall surfaces. | m² | 191.37 | 15 | 37 | forman 1 | own force
49 | Plastic paint to chip wooden ceiling | m² | 135.3 | 7 | 38 | forman 1 | own force
50 | HWB | No. | 2 | 1 | 44 | plumber | own force
51 | WC | No. | 2 | 1 | 44 | plumber | own force
52 | Toilet paper holder | No. | 2 | 1 | 44 | plumber | own force
53 | Soap holder | No. | 4 | 1 | 44 | plumber | own force
54 | Enameled cast iron shower unit | No. | 2 | 1 | 42 | plumber | own force
55 | Single boul sink out of stainless steel, | No. | 2 | 1 | 44 | plumber | own force
56 | floor drains , Size: - Dia. 50 mm | No. | 2 | 1 | 42 | plumber | own force
57 | Glass mirror | No. | 2 | 1 | 47 | plumber | own force
58 | GS Pipe Dia. 15 mm | m | 12 | 3 | 36 | plumber | own force
59 | Gate valve Dia. 15 mm | No. | 4 | 1 | 58 | plumber | own force
60 | PVC Pipe Dia. 50 mm | m | 7 | 3 | 36 | plumber | own force
61 | PVC Pipe Dia. 110 mm | m | 3.5 | 3 | 36 | plumber | own force
62 | Down pipe, G-28: 100 x 80 mm | m | 24 | 3 | 37 | plumber | own force
63 | Manhole, Size: 600 x 600 x 700 mm inner diameter | No. | 3 | 7 | 45 | plumber | own force
64 | Supply and install PVC conduit of 36 mm diameter | m | 90 | 2 | 36 | electrician | own force
65 | Flush mounting distribution board MDB1 | No. | 1 | 1 | 36 | electrician | own force
66 | flush mounted light points | No. | 15 | 7 | 36 | electrician | own force
67 | single switch | No. | 10 | 3 | 47 | electrician | own force
68 | two-way switch | No. | 10 | 3 | 47 | electrician | own force
69 | socket outlet points | No. | 10 | 7 | 36 | electrician | own force
70 | socket outlet of 10A/1P, | No. | 10 | 3 | 47 | electrician | own force
71 | Fluorescent fitting type | No. | 5 | 2 | 46,49 | electrician | own force
72 | Incandescent fitting | No. | 10 | 2 | 46,49 | electrician | own force
| Project completion |  |  |  |  | Project manager | own force
Indirect costs
| Site office | 1500 | birr/mon
| Project manager | 6000 | birr/mon
| office and site engineers | 6000 | birr/mon
| Car for service | 7500 | birr/mon
| other expenses | 10000 | birr/mon

## Tracking
1 | Data Date | 2007-10-15
ID No | Task | Unit | Estimated Qty | Actual Start Date | Progress | Resource
Site handover
1 | Site clearing | m² | 250.74 | 2007-10-05 | 100% | dl
2 | Trench excavation | m³ | 54.15 | 2007-10-07 | 30% | dl
3 | Backfill under hard core | m³ | 26.06
4 | 250 mm thick basaltic stone hardcore | m² | 130.29
5 | Lean concrete Under masonry | m² | 27.06 | 2007-10-10 | 10% | dl,cem,san,grav,mix,mas
6 | C-25 concrete In grade beams | m³ | 5.69
7 | C-25 concrete In 100 mm thick floor slab | m² | 161.68
8 | Form work To grade beams, errection | m² | 55.96
9 | Form work To grade beams, dismantling | m² | 55.96
10 | Dia 8 mm deformed bar | kg | 312.9585
11 | Dia 12 mm deformed bar | kg | 155.4
12 | 400 mm thick basaltic stone masonry, below ground surface. | m³ | 54.15
13 | 400 mm thick basaltic stone masonry, above ground surface. | m³ | 16.25
14 | C-25 In elevation columns | m³ | 1.98
15 | C-25 In roof beams | m³ | 4.54
16 | Form work For elevation columns | m² | 10.32
17 | Form work For roof beams, errection | m² | 55.96
18 | Form work For roof beams, dismantling | m² | 56.96
19 | Dia 8 mm deformed bar | kg | 77.6965
20 | Dia 12 mm deformed bar | kg | 217.0272
21 | Class C, 200 mm thick HCB wall | m² | 229.25
22 | Class C, 100 mm thick HCB wall | m² | 54.53
23 | Roof cover, USG 30 | m² | 223.26
24 | G-30 galvanized flat metal sheet gutter | m | 48.8
25 | Eucalyptus wood Horizontal truss members. Size dia.100 mm | m | 358.15
26 | Eucalyptus wood vertical & diagonal truss members.Size dia.80 mm | m | 105.4
27 | Sawn zigba wood roof purlins placed at c/c 900 mm. Size 50 x 70 mm | m | 341.6
28 | 8 mm thick chip wood ceilings | m² | 135.3
29 | 0.8 mm thick ribbed sheet metal soffit cover | m² | 26.32
30 | Tid wood Facia board | m | 68.2
31 | FD Type D1: Size 900 x 2100 mm | No. | 3
32 | MD Type D1: Size 900 x 2100 mm | No. | 5
33 | MD Type D2: Size 700 x 2100 mm | No. | 5
34 | MW Type W1: 1000 x 1200 mm | No. | 5
35 | MW Type W2: 1800 x 1200 mm | No. | 5
36 | 3 coats of Plaster To internal wall surface | m² | 324.03
37 | 3 coats of Plaster To external wall surface | m² | 191.37
38 | Two coats of plastering | m² | 62.25
39 | 48 mm thick trowel finished cement sand screed (1:3) to receive PVC tile | m² | 18
40 | PVC floor tile, 2 mm thick | m² | 18
41 | PVC skirting, 60 mm wide | m² | 54.6
42 | Terrazzo floor tile, 20 mm thick. | m² | 54
43 | Terrazzo skirting stuck to wall, 100 mm wide. | m² | 85.8
44 | 6 mm thick white ceramic wall tile | m² | 62.25
45 | 600 mm wide stone pavement around the building. | m² | 23.28
46 | 4 mm thick clear glass |  | 10.26
47 | Plastic paint to internal wall surfaces flushed finished | m² | 324.03
48 | Plastick paint to external plastered wall surfaces. | m² | 191.37
49 | Plastic paint to chip wooden ceiling | m² | 135.3
50 | HWB | No. | 2
51 | WC | No. | 2
52 | Toilet paper holder | No. | 2
53 | Soap holder | No. | 4
54 | Enameled cast iron shower unit | No. | 2
55 | Single boul sink out of stainless steel, | No. | 2
56 | floor drains , Size: - Dia. 50 mm | No. | 2
57 | Glass mirror | No. | 2
58 | GS Pipe Dia. 15 mm | m | 12
59 | Gate valve Dia. 15 mm | No. | 4
60 | PVC Pipe Dia. 50 mm | m | 7
61 | PVC Pipe Dia. 110 mm | m | 3.5
62 | Down pipe, G-28: 100 x 80 mm | m | 24
63 | Manhole, Size: 600 x 600 x 700 mm inner diameter | No. | 3
64 | Supply and install PVC conduit of 36 mm diameter | m | 90
65 | Flush mounting distribution board MDB1 | No. | 1
66 | flush mounted light points | No. | 15
67 | single switch | No. | 10
68 | two-way switch | No. | 10
69 | socket outlet points | No. | 10
70 | socket outlet of 10A/1P, | No. | 10
71 | Fluorescent fitting type | No. | 5
72 | Incandescent fitting | No. | 10
Project completion